## Template
ID | Name | Role | Department | Contact Information | Interest/ Expectation | Influence Level | Engagement Strategy | Notes
1 | John Smith | Project Manager | Project Management | john.smith@construction.com | Ensure overall project success | High | Daily updates, weekly meetings | Overall project coordination
2 | Jane Doe | Architect | Design | jane.doe@architecture.com | Ensure design meets client requirements | High | Weekly design review meetings | Key decision-maker in design
3 | Mike Johnson | Site Supervisor | Construction | mike.johnson@site.com | Ensure on-site work is progressing according to plan | High | Daily briefings, site visits | Manages on-site construction activities
4 | Susan Lee | Structural Engineer | Engineering | susan.lee@engineering.com | Ensure structural integrity of the construction | Medium | Weekly engineering updates | Provides structural expertise
5 | Tom Brown | Safety Officer | Safety | tom.brown@safety.com | Ensure all safety regulations are followed | High | Daily safety briefings, inspections | Ensures safety compliance
6 | Lisa Green | Procurement Manager | Procurement | lisa.green@procurement.com | Ensure timely delivery of materials | Medium | Bi-weekly procurement meetings | Manages supply chain and procurement
7 | Bob White | Financial Controller | Finance | bob.white@finance.com | Ensure project stays within budget | High | Monthly financial reports, budget reviews | Controls budget allocations
8 | Karen Black | Client Representative | Client | karen.black@client.com | Ensure project meets client's expectations | High | Weekly client updates, site visits | Client liaison
9 | Emily Davis | Legal Advisor | Legal | emily.davis@legal.com | Ensure all legal requirements are met | Medium | Monthly legal reviews | Ensures legal compliance
10 | Richard Harris | Environmental Consultant | Environmental | richard.harris@enviro.com | Ensure project meets environmental regulations | Medium | Monthly environmental assessments | Provides environmental expertise
| i | This is a free template, you can use this template to plan a small project with 15 items, check our premium templates for unlocked version with more features.
4 View Details
Stakeholder Register Template
Excelx.com | Powered by Analysistabs®

## Lists
Influence Level
High
Medium
Low

## Intro
| Stakeholder Register Template | Get our Premium Project Management Templates
Free Excel Template by analysistabs.com
Info 4 | Free Excel Stakeholder Register Template for effectively managing project stakeholders, enhancing communication, and ensuring successful project delivery.
Usage 4 | Helps manage finances by tracking income and expenses, allowing customization of data and formulas for effective budgeting.
Share 4 | Excelx.com powered by Analysistabs ™ is developing Free and Premium l Project Management Templates. Please do not share this downloaded file. Instead, you can share our free template page link with your colleagues and friends, it helps us to create better tools and more templates.
Email 4 | Please share your feedback or ask questions, Email: info@analysistabs.com
Please Visit us
Visit us for more Free Templates and Premium Templates |  |  | Progress | 1 days | TOTAL TASKS 4 | 1
|  |  | #REF! | 0 | Completed | #REF!
|  |  | #REF! | 0 | In progress | #REF!
|  |  |  | #NAME? | Not Started | #REF!
i Please do not delete this worksheet. Instead, you can hide the sheet.
4 Download Now
*
1

## License
License Terms
4 | Analysistabs® License Agreement
This Template/Excel File and sample data is created by Analysistabs®
4 | Single User License: Allows 1 (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this template for their personal use only
4 | You can share the template page link:(https://analysistabs.com/project/management/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
Link: | https://analysistabs.com/project/management/
Hello! it’s a sheet
Calculations ->
|  | Progress | 1 days | 0 | TOTAL TASKS 4 | 1
|  | #REF! | 0 | 0 | Completed | #REF!
|  | #REF! | 0 | 0 | In progress | #REF!
|  | 0 | #NAME? | 0 | Not Started | #REF!
Disclaimer: The information on Excelx.com, including articles, examples, and templates, is for your reference only. We try our best to keep it accurate, but we can't guarantee it's always perfect. If you use this information, you take full responsibility for any risks.
Excel Blog