## Monthly Gantt Chart
| Monthly Gantt Chart |  |  |  |  | Gantt Start Date |  | Project Objective: To design, develop, and launch a unified global retail platform across three continents, integrating localized payment systems and a centralized inventory engine to drive a 40% increase in international reach. | [6 empty] | 54.8% |  | 0.548
| Global Omni-Channel Expansion 2026 |  |  |  |  | 2026-01-01 | [10 empty] | 0.452
Task Table |  |  |  | (Months) |  | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026
ID | Task Name / Phase | Owner | Start Date | Duration | Progress | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
1 | PHASE 1: STRATEGIC PLANNING & ARCHITECTURE | Sarah Jenkins | 2026-01-01 | 5 | 100%
2 | Global Market Research & Compliance Audit | Mike Ross | 2026-02-01 | 3 | 100%
3 | Core System Architecture & Cloud Scaling Plan | David Kim | 2026-04-01 | 2 | 100%
4 | Stakeholder Alignment & Funding Approval | Elena Rodriguez | 2026-03-01 | 2 | 100%
5 | PHASE 2: DESIGN & LOCALIZATION | Kevin Vance | 2026-02-15 | 6 | 80%
6 | UX/UI Global Design System Development | James Holden | 2026-02-15 | 4 | 50%
7 | Multi-Language & Currency Interface Design | Naomi Nagata | 2026-03-01 | 4 | 95%
8 | Regional User Persona & Feedback Loops | Amos Burton | 2026-05-15 | 3 | 100%
9 | PHASE 3: CORE DEVELOPMENT (PARALLEL WORK) | Alex Kamal | 2026-03-15 | 5 | 65%
10 | Centralized Inventory Engine Development | Bobbie Draper | 2026-03-15 | 3 | 100%
11 | Localized Payment Gateway API Integration | Mark Watney | 2026-04-01 | 3 | 80%
12 | Frontend Framework Implementation (Global) | Rick Martinez | 2026-05-01 | 2 | 50%
13 | Mobile App Synchronization Layer | Beth Johanssen | 2026-06-01 | 2 | 20%
14 | PHASE 4: MARKETING & CONTENT STRATEGY | Chris Beck | 2026-04-01 | 6 | 40%
15 | International SEO & Keyword Strategy | Melissa Lewis | 2026-04-01 | 3 | 100%
16 | Global Content Production & Translation | Peggy Whitson | 2026-05-15 | 4 | 60%
17 | Influencer & Social Media Campaign Setup | Scott Kelly | 2026-08-01 | 2 | 10%
18 | PHASE 5: QUALITY ASSURANCE & PILOT | Buzz Aldrin | 2026-07-01 | 4 | 25%
19 | Cross-Browser & Security Penetration Testing | Tim Peake | 2026-07-01 | 2 | 80%
20 | Beta Launch (European Market Only) | Chris Hadfield | 2026-09-01 | 1 | 10%
21 | Bug Fixing & Performance Optimization | Gene Kranz | 2026-09-15 | 2 | 5%
22 | PHASE 6: FINAL ROLLOUT & SCALE | Flight Director | 2026-11-01 | 2 | 0%
23 | Global Production Deployment | Nav Officer | 2026-11-01 | 1 | 0%
24 | Executive Post-Launch Review | Ground Lead | 2026-11-15 | 1 | 0%
25 | Ongoing Support & Hypercare Phase | Propulsion Eng | 2026-12-01 | 1 | 0%
Monthly Roadmap: 12-month annual plan
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License-Disclaimer
License Terms
4 | Analysistabs® License Agreement
This Template/Excel File and sample data is created by Excelx.com Powered by Analysistabs®
4 | Single User License: Allows 1 (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this file/template for their personal use only
4 | You can share the web page link:(https://excelx.com/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | Excel Files/ templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
Disclaimer: The information on Excelx.com, including articles, examples, and templates, is for your reference only. We try our best to keep it accurate, but we can't guarantee it's always perfect. If you use this information, you take full responsibility for any risks.
Excel Blog