## Monthly Gantt Chart
| Monthly Gantt Chart |  |  |  |  | Gantt Start Date |  |  |  | 🎯 |  | Project Objective: A multi-year initiative to overhaul legacy ERP systems, migrate global data centers to a unified cloud architecture, and deploy AI-driven logistics across four international hubs. | [14 empty] | 23.4% |  | 0.234
| Enterprise Digital Transformation & Global Infrastructure 2.0 |  |  |  |  | 2026-01-01 | [22 empty] | 0.766
Task Table |  |  |  | (Months) |  | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027
ID | Task Name / Phase | Owner | Start Date | Duration | Progress | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
1 | PHASE 1: FOUNDATION & CLOUD MIGRATION | Sarah Jenkins | 2026-01-01 | 10 | 85%
2 | Legacy System Audit & Data Cleaning | Mike Ross | 2026-01-01 | 4 | 100%
3 | Global Cloud Infrastructure Setup | David Kim | 2026-03-01 | 6 | 90%
4 | Security & Compliance Framework v2 | Elena Rodriguez | 2026-05-01 | 5 | 40%
5 | PHASE 2: ERP SYSTEM OVERHAUL (CORE) | Kevin Vance | 2026-06-01 | 12 | 30%
6 | Financial Module Development & Testing | James Holden | 2026-06-01 | 6 | 60%
7 | Supply Chain & Inventory Integration | Naomi Nagata | 2026-08-01 | 8 | 25%
8 | Human Capital Management (HCM) Rollout | Amos Burton | 2026-10-01 | 5 | 10%
9 | PHASE 3: AI & DATA ANALYTICS LAYER | Alex Kamal | 2027-01-01 | 10 | 0%
10 | Predictive Analytics Engine Development | Bobbie Draper | 2027-01-01 | 6 | 0%
11 | Automated Logistics & Warehouse AI | Mark Watney | 2027-03-01 | 7 | 0%
12 | Customer Sentiment Analysis Tools | Rick Martinez | 2027-05-01 | 4 | 0%
13 | PHASE 4: REGIONAL DEPLOYMENT (WAVE 1) | Beth Johanssen | 2026-06-01 | 18 | 45%
14 | North America & EMEA Market Sync | Chris Beck | 2026-06-01 | 9 | 100%
15 | APAC Region Integration & Training | Melissa Lewis | 2027-03-01 | 8 | 0%
16 | LATAM Expansion & Localization | Peggy Whitson | 2027-08-01 | 6 | 0%
17 | PHASE 5: MARKETING & BRAND TRANSITION | Scott Kelly | 2027-01-01 | 12 | 0%
18 | Global Rebranding Campaign Strategy | Buzz Aldrin | 2027-01-01 | 4 | 0%
19 | Digital Presence & Omni-channel Launch | Tim Peake | 2027-04-01 | 6 | 0%
20 | Post-Launch Market Saturation Study | Chris Hadfield | 2027-09-01 | 4 | 0%
21 | PHASE 6: OPTIMIZATION & SUSTAINABILITY | Gene Kranz | 2027-06-01 | 7 | 0%
22 | Performance Tuning & System Hardening | Flight Director | 2027-06-01 | 4 | 0%
23 | User Adoption Surveys & Refinements | Nav Officer | 2027-08-01 | 4 | 0%
24 | Final Global Transition Review | Ground Lead | 2027-11-01 | 2 | 0%
25 | Project Closure & Handover to Ops | Propulsion Eng | 2027-12-01 | 1 | 0%
24-month (2-year) strategic roadmap
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License-Disclaimer
License Terms
4 | Analysistabs® License Agreement
This Template/Excel File and sample data is created by Excelx.com Powered by Analysistabs®
4 | Single User License: Allows 1 (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this file/template for their personal use only
4 | You can share the web page link:(https://excelx.com/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | Excel Files/ templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
Disclaimer: The information on Excelx.com, including articles, examples, and templates, is for your reference only. We try our best to keep it accurate, but we can't guarantee it's always perfect. If you use this information, you take full responsibility for any risks.
Excel Blog