## Weekly Gantt Chart
| Weekly Gantt Chart |  |  |  |  | Gantt Start Date |  |  |  |  | Project Objective: Redesign and rebuild the company's e-commerce website to improve user experience, modernize the tech stack, and drive better conversion and performance. | [14 empty] | 57.6% |  |  | 0.576
| E-Commerce Platform Redesign |  |  |  |  | 2026-03-01 | [22 empty] | 0.424
Task Table |  |  |  | (Weeks) |  | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03
ID | Task Name | Owner | Start Date | Duration | Progress | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
1 | PHASE 1: STRATEGY & DISCOVERY | Sarah Jenkins | 2026-03-01 | 4 | 100%
2 | Project Kickoff & Stakeholder Alignment | Mike Ross | 2026-03-01 | 2 | 100%
3 | Market Research & Gap Analysis | David Kim | 2026-03-01 | 3 | 100%
4 | Technical & Business Requirements | Elena Rodriguez | 2026-03-08 | 3 | 100%
5 | User Journey Mapping & Personas | Kevin Vance | 2026-03-15 | 2 | 100%
6 | PHASE 2: DESIGN & USER EXPERIENCE | James Holden | 2026-03-22 | 6 | 85%
7 | Information Architecture & Sitemap | Naomi Nagata | 2026-03-22 | 2 | 100%
8 | Wireframes & Low-Fi Prototypes | Amos Burton | 2026-03-29 | 3 | 90%
9 | UI Design System & Brand Guidelines | Alex Kamal | 2026-04-05 | 4 | 75%
10 | High-Fidelity Mockups & Prototyping | Bobbie Draper | 2026-04-12 | 3 | 60%
11 | PHASE 3: TECHNICAL FOUNDATION | Mark Watney | 2026-03-22 | 6 | 70%
12 | Backend API Architecture Design | Rick Martinez | 2026-03-22 | 3 | 100%
13 | Database Schema & Environment Setup | Beth Johanssen | 2026-03-29 | 3 | 80%
14 | Frontend Framework Implementation | Chris Beck | 2026-04-05 | 4 | 50%
15 | Security Protocols & Auth Setup | Melissa Lewis | 2026-04-12 | 3 | 40%
16 | PHASE 4: CORE DEVELOPMENT | Peggy Whitson | 2026-04-26 | 10 | 30%
17 | Product Catalog & Search Module | Scott Kelly | 2026-04-26 | 5 | 50%
18 | Shopping Cart & Checkout Engine | Buzz Aldrin | 2026-05-10 | 5 | 20%
19 | Payment Gateway Integration | Tim Peake | 2026-05-24 | 4 | 10%
20 | CMS Integration & Content Migration | Chris Hadfield | 2026-05-31 | 5 | 0%
21 | Email & Notification Systems | Gene Kranz | 2026-06-14 | 3 | 0%
22 | PHASE 5: QUALITY & DEPLOYMENT | Flight Director | 2026-06-07 | 8 | 20%
23 | Comprehensive Unit & Integration Testing | Nav Officer | 2026-06-07 | 6 | 50%
24 | UAT & Final Stakeholder Sign-off | Ground Lead | 2026-07-19 | 2 | 10%
25 | Production Launch & Hypercare | Propulsion Eng | 2026-07-26 | 2 | 0%
Weekly Roadmap: 24-week project plan
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License-Disclaimer
License Terms
4 | Analysistabs® License Agreement
This Template/Excel File and sample data is created by Excelx.com Powered by Analysistabs®
4 | Single User License: Allows 1 (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this file/template for their personal use only
4 | You can share the web page link:(https://excelx.com/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | Excel Files/ templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
Disclaimer: The information on Excelx.com, including articles, examples, and templates, is for your reference only. We try our best to keep it accurate, but we can't guarantee it's always perfect. If you use this information, you take full responsibility for any risks.
Excel Blog