## Intro
X. | Excelx.com |  | TEMPLATE GUIDE
One-Page RACI
Category: Standard RACI
📄 | ABOUT THIS TEMPLATE
Fits on a single printed page. Perfect for kickoff meetings.
✅ | WHAT'S INCLUDED
| Colour-coded matrix | R/A/C/I cells auto-colour via conditional formatting
| Dropdown validation | Click any RACI cell to select from a dropdown
| Workload Analysis | COUNTIF formulas count assignments per person
| Role Definitions | Coloured legend with descriptions at bottom
| Project Details | Pre-formatted header with project info fields
| Print-ready | Landscape layout, fit-to-width for A4
📝 | HOW TO USE
1. Go to the RACI template sheet (same name in the main workbook)
2. Fill in Project Details — project name, manager, date
3. Replace team member names in the header row
4. Edit tasks to match your project — add/delete rows as needed
5. Assign roles — click each cell, select from the dropdown
6. Check the Workload Analysis — it auto-calculates
7. Review Role Definitions at the bottom for guidance
🎨 | RACI COLOR REFERENCE
R | Responsible | Does the work
A | Accountable | Owns the outcome
C | Consulted | Gives input
I | Informed | Kept in the loop
👨‍💼 PNRao – Project Management Expert ¦ 🌐 ExcelX.com ¦ 📊 Explore 120+ Premium Templates

## One-Page RACI
X. | Excelx.com |  |  | ONE-PAGE RACI
| Free Excel Templates |  |  | Print-Ready Single Page
📁 | PROJECT DETAILS
| Project Name |  |  | One-Page RACI
Project Manager
Date
| Version |  |  | 1.0
🗂 | RESPONSIBILITY MATRIX (RACI)
| Task / Activity | Deliverable | PM | Sponsor | Team Lead | Developer | QA | Stakeholder
Project Tasks
1 | Task 1: Define requirements | Requirements doc | R | A | C | C |  | I
2 | Task 2: Create design | Design doc | A | I | R | C
3 | Task 3: Develop solution | Working code | A |  | C | R | I
4 | Task 4: Test solution | Test report | I |  | C | C | R
5 | Task 5: Deploy to production | Live system | A | I | R | C | C
6 | Task 6: User training | Training materials | R | I | C |  |  | A
7 | Task 7: Documentation | User guide | A |  | R | C
8 | Task 8: Handover | Handover pack | R | A | C | I | I | I
9 | Task 9: Post-launch support | Support log | A |  | R |  | C | I
10 | Task 10: Project closure | Closure report | R | A | I | I | I | I
📊 | WORKLOAD ANALYSIS (Auto-Calculated)
Count
R | Responsible |  | 4 | 0 | 4 | 1 | 1 | 0
A | Accountable |  | 5 | 3 | 0 | 0 | 0 | 1
C | Consulted |  | 0 | 0 | 5 | 5 | 2 | 0
I | Informed |  | 1 | 3 | 1 | 2 | 3 | 4
| Total |  | 10 | 6 | 10 | 8 | 6 | 5
📖 | ROLE DEFINITIONS
R | Responsible |  | Does the work — the person(s) who complete the task
A | Accountable |  | Owns the outcome — ONE person who approves. Only one A per task
C | Consulted |  | Gives input — experts whose opinion is sought. Two-way
I | Informed |  | Kept in the loop — notified of progress. One-way
👨‍💼 PNRao – Project Management Expert │ 🌐 ExcelX.com │ 🔓 Get 120+ Premium Templates
Get 120+ Premium Templates
Upgrade Now

## License-Disclaimer
License Terms
4 | Analysistabs® License Agreement
This Template/Excel File and sample data is created by Excelx.com Powered by Analysistabs®
4 | Single User License: Allows 1 (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this file/template for their personal use only
4 | You can share the web page link:(https://excelx.com/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | Excel Files/ templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
Disclaimer: The information on Excelx.com, including articles, examples, and templates, is for your reference only. We try our best to keep it accurate, but we can't guarantee it's always perfect. If you use this information, you take full responsibility for any risks.
Excel Blog