## 17 Agile
| Agile Scrum Project Planner | [7 empty] | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | IN PROGRESS | [6 empty] | NOT STARTED | [6 empty] | 🎢 Overall Progress |  |  | 45.6% |  |  | 0.456
| Sprint-based Roadmap: 4-sprint release cycle | [7 empty] | 25 | [6 empty] | 9 | [6 empty] | 4 | [6 empty] | 12
| Project Nimbus: Mobile App v2.0 | [41 empty] | 0.544
Project Details | Project Name | Project Nimbus: Mobile App v2.0 |  |  |  |  | Sprint Length | 2 weeks | 🎯 Project Objective | [6 empty] | Deliver v2.0 with offline mode, push notifications, and redesigned onboarding across iOS and Android in 4 two-week sprints.
| Product Owner | Emily Davis |  |  |  |  | Start Date | 2026-05-04 | [29 empty] | Completed | 9
| Scrum Master | Derek Huang |  |  | Created On | 2026-04-20 | Release Date | 2026-06-26 | [29 empty] | In progress | 4
| Created By | Derek Huang |  |  | Last Updated | 2026-04-20 | Current Sprint | Sprint 3 | [29 empty] | Not started | 12
Task Table | [8 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | User Story | Sprint # | Story Pts | Assigned To | Start Date | End Date | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
US-01 | Set up CI/CD pipeline for mobile | Sprint 1 | 3 | Derek Huang | 2026-05-04 | 2026-05-06 | 100% | Completed
US-02 | Configure push notification (Firebase) | Sprint 1 | 5 | Raj Kapoor | 2026-05-04 | 2026-05-08 | 100% | Completed
US-03 | Design new onboarding wireframes | Sprint 1 | 3 | Maya Torres | 2026-05-04 | 2026-05-07 | 100% | Completed
US-04 | Build onboarding screen 1: Welcome | Sprint 1 | 3 | Raj Kapoor | 2026-05-07 | 2026-05-11 | 100% | Completed
US-05 | Build onboarding screen 2: Setup | Sprint 1 | 3 | Sophie Lin | 2026-05-07 | 2026-05-11 | 100% | Completed
US-06 | API for user preferences sync | Sprint 1 | 5 | Tom Nakamura | 2026-05-08 | 2026-05-14 | 100% | Completed
US-07 | Sprint 1 review & retro | Sprint 1 | 0 | Derek Huang | 2026-05-15 | 2026-05-15 | 100% | Completed
US-08 | Local SQLite for offline storage | Sprint 2 | 8 | Tom Nakamura | 2026-05-18 | 2026-05-25 | 80% | In progress
US-09 | Offline sync & conflict resolution | Sprint 2 | 8 | Raj Kapoor | 2026-05-18 | 2026-05-26 | 70% | In progress
US-10 | Push notification opt-in flow | Sprint 2 | 5 | Sophie Lin | 2026-05-18 | 2026-05-22 | 100% | Completed
US-11 | Notification templates: orders, promos | Sprint 2 | 3 | Maya Torres | 2026-05-20 | 2026-05-22 | 100% | Completed
US-12 | Offline indicator banner & retry | Sprint 2 | 3 | Sophie Lin | 2026-05-22 | 2026-05-26 | 60% | In progress
US-13 | Unit tests for offline sync | Sprint 2 | 3 | Tom Nakamura | 2026-05-25 | 2026-05-28 | 30% | In progress
US-14 | Sprint 2 review & retro | Sprint 2 | 0 | Derek Huang | 2026-05-29 | 2026-05-29 | 0% | Not started
US-15 | Redesign home screen navigation | Sprint 3 | 5 | Maya Torres | 2026-05-22 | 2026-05-26 | 0% | Not started
US-16 | Analytics SDK (Mixpanel) | Sprint 3 | 3 | Sophie Lin | 2026-05-24 | 2026-05-26 | 0% | Not started
US-17 | Performance & memory optimization | Sprint 3 | 5 | Tom Nakamura | 2026-05-25 | 2026-05-30 | 0% | Not started
US-18 | Accessibility audit & fixes | Sprint 3 | 3 | Maya Torres | 2026-05-29 | 2026-05-31 | 0% | Not started
US-19 | Sprint 3 review & retro | Sprint 3 | 0 | Derek Huang | 2026-06-02 | 2026-06-02 | 0% | Not started
US-20 | Beta to TestFlight & Play Console | Sprint 4 | 3 | Derek Huang | 2026-06-05 | 2026-06-06 | 0% | Not started
US-21 | Beta feedback collection & triage | Sprint 4 | 3 | Aisha Patel | 2026-05-27 | 2026-05-30 | 0% | Not started
US-22 | App Store & Play listing update | Sprint 4 | 2 | Maya Torres | 2026-05-30 | 2026-06-02 | 0% | Not started
US-23 | Final regression testing | Sprint 4 | 3 | Sophie Lin | 2026-06-02 | 2026-06-04 | 0% | Not started
US-24 | Production release submission | Sprint 4 | 2 | Derek Huang | 2026-06-04 | 2026-06-05 | 0% | Not started
US-25 | Post-launch monitoring & hotfix | Sprint 4 | 3 | Tom Nakamura | 2026-06-05 | 2026-06-06 | 0% | Not started
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Blank Template
| Agile Scrum Project Planner | [7 empty] | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | IN PROGRESS | [6 empty] | NOT STARTED | [6 empty] | 🎢 Overall Progress |  |  | 0% |  |  | 0
| Sprint-based Roadmap: 4-sprint release cycle | [7 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
1
Project Details | Project Name | [5 empty] | Sprint Length |  | 🎯 Project Objective
| Product Owner | [5 empty] | Start Date | [30 empty] | Completed | 0
| Scrum Master |  |  |  | Created On |  | Release Date | [30 empty] | In progress | 0
| Created By |  |  |  | Last Updated |  | Current Sprint | [30 empty] | Not started | 0
Task Table | [8 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | User Story | Sprint # | Story Pts | Assigned To | Start Date | End Date | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Instructions
Agile Scrum Project Planner - Instructions
FIELD | WHAT TO ENTER
Project Name | Enter your project name (e.g., Website Redesign, ERP Migration).
Product Owner | Name of the product owner responsible for the backlog.
Scrum Master | Name of the Scrum Master facilitating sprints.
Start Date | Project start date (MM/DD/YYYY).
Release Date | Project end date (MM/DD/YYYY).
Sprint Length | Current sprint number or sprint length.
Current Sprint | Current sprint number or sprint length.
🎯 Project Objective | 1-2 sentence project goal and measurable success criteria.
Created By | Name of the person who created this plan.
Created On | Date this plan was created (MM/DD/YYYY).
Last Updated | Date of last update (MM/DD/YYYY).
Task Table Columns
ID | Unique task identifier (e.g., WF-01). Keep sequential.
User Story | Clear, action-oriented task description.
Sprint # | Sprint number this task belongs to.
Story Pts | Story points estimate (e.g., 1, 2, 3, 5, 8, 13).
Assigned To | Team member responsible for this task.
Start Date | Task start date (MM/DD/YYYY).
End Date | Task end date (MM/DD/YYYY).
Progress | Enter manually (0% to 100%). Update daily.
Status | Auto-calculated. Do not edit.
Gantt Chart | Auto-generated from Start/End dates. Do not edit. Bars update automatically.
Grey / Locked Cells
Light grey cells | Contain formulas - auto-calculated from your entries.
Formula bar blank | By design - formulas are hidden for protection.
Cannot edit | These cells are locked. Only white cells are editable.
Tips
Phase rows | Bold colored rows are section headers. Enter tasks below them.
Dropdowns | Click cells with small arrows to see available options.
Dates | Use MM/DD/YYYY format for all date fields.
Progress | Enter manually (0% to 100%). Update daily as work progresses.
Status | Auto-calculated from Progress. 100%=Completed, 1-99%=In progress, 0%=Not started.
Save often | File > Save As to create backup versions.
Need More Features?
More tasks | FREE version supports 25 tasks. Premium = unlimited tasks with auto-expanding rows.
Longer Gantt | FREE = 5-week Gantt. Premium = 9-week dynamic view with zoom in/out.
Unlimited Projects | Premium supports unlimited project sheets with one-click duplication.
Fully Unlocked | All cells editable. No locked sheets, no hidden formulas, no restrictions.
Fully Customizable | Easily customize colors, layout, and fields to suit any project type or industry.
Get Premium Template | Visit analysistabs.org/product/simple-multiple-project-tracking-template-excel/
Excel PM Templates by PNRao ¦ Excelx.com ¦ Powered by Analysistabs®

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms

## Analysistabs (hidden)
1
DO NOT DELETE OR MODIFY THIS SHEET
WARNING — SYSTEM SHEET
This sheet is required for the template to function correctly.
It contains essential configuration used by formulas, conditional formatting,
Gantt chart rendering, progress bars, and KPI calculations.
| If this sheet is deleted or modified: | 1
| • Gantt chart bars will stop rendering | 1
| • Progress bars will show errors | 1
• KPI cards will display #REF! errors
• Conditional formatting will break
• Auto-calculated fields will stop working
This sheet will be hidden when the template is exported.
Users will not see this sheet in the downloaded file.
Analysistabs® ¦ Excelx.com ¦ Template Configuration Sheet