## Project Plan
| Project Planner with Gantt Chart | [6 empty] | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | IN PROGRESS | [6 empty] | NOT STARTED | [6 empty] | 🎢 Overall Progress |  |  | 41.6% |  |  | 0.416
| Complete Project Management: Plan + Budget + Risk + RACI + Dashboard | [6 empty] | 25 | [6 empty] | 7 | [6 empty] | 9 | [6 empty] | 7
| Project Nova: Digital Workplace Transformation | [40 empty] | 0.584
Project Details | Project Name | Project Nova: Digital Workplace Transformation |  |  |  | Start Date | 2026-05-04 | 🎯 Project Objective | [6 empty] | Deploy unified digital workplace (Teams, SharePoint, Power Platform) across 5 departments, migrating from legacy intranet and email systems.
| Project Manager | Catherine Reyes |  |  |  | End Date | 2026-06-05 | [29 empty] | Completed | 7
| Department | Digital & IT | Created On | 2026-05-04 |  | Budget | 340000 | [29 empty] | In progress | 9
| Created By | Catherine Reyes | Last Updated | 2026-05-04 |  | Days Left | 28 | [29 empty] | Not started | 7
Task Table | [7 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[8 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
WBS | Phase/Task Name | Assigned To | Planned Start | Planned End | Budget | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
PHASE 1: ASSESSMENT & PLANNING
NV-01 | Current state assessment & gap analysis | Catherine Reyes | 2026-05-04 | 2026-05-07 | 15000 | 100% | Completed
NV-02 | Stakeholder interviews & requirements | Omar Hassan | 2026-05-04 | 2026-05-08 | 8000 | 100% | Completed
NV-03 | Vendor evaluation & licensing review | Catherine Reyes | 2026-05-06 | 2026-05-09 | 5000 | 100% | Completed
NV-04 | Project charter & roadmap sign-off | Catherine Reyes | 2026-05-08 | 2026-05-09 | 2000 | 100% | Completed
NV-05 | Infrastructure readiness check | Leo Park | 2026-05-09 | 2026-05-12 | 12000 | 100% | Completed
PHASE 2: DESIGN & CONFIGURATION
NV-06 | Information architecture design | Mei Zhang | 2026-05-11 | 2026-05-15 | 18000 | 100% | Completed
NV-07 | SharePoint site structure & permissions | Leo Park | 2026-05-12 | 2026-05-16 | 15000 | 100% | Completed
NV-08 | Teams channels & governance policies | Omar Hassan | 2026-05-13 | 2026-05-16 | 10000 | 80% | In progress
NV-09 | Power Platform workflow prototypes | Mei Zhang | 2026-05-14 | 2026-05-19 | 20000 | 60% | In progress
NV-10 | Branding & UX customization | Mei Zhang | 2026-05-15 | 2026-05-20 | 8000 | 50% | In progress
PHASE 3: MIGRATION & BUILD
NV-11 | Email migration (Exchange to M365) | Leo Park | 2026-05-18 | 2026-05-22 | 25000 | 40% | In progress
NV-12 | Document migration (file shares to SPO) | Leo Park | 2026-05-19 | 2026-05-26 | 22000 | 30% | In progress
NV-13 | Intranet content migration | Omar Hassan | 2026-05-20 | 2026-05-27 | 18000 | 20% | In progress
NV-14 | Power Automate flows deployment | Mei Zhang | 2026-05-21 | 2026-05-28 | 15000 | 15% | In progress
NV-15 | Custom app development (Power Apps) | Mei Zhang | 2026-05-22 | 2026-05-29 | 30000 | 10% | In progress
NV-16 | SSO & security configuration | Leo Park | 2026-05-22 | 2026-05-27 | 12000 | 10%
PHASE 4: TESTING & TRAINING
NV-17 | Integration testing & validation | Leo Park | 2026-05-26 | 2026-05-29 | 8000 | 25% | In progress
NV-18 | UAT with department champions | Omar Hassan | 2026-05-27 | 2026-06-01 | 5000 | 0% | Not started
NV-19 | Training materials & video tutorials | Catherine Reyes | 2026-05-28 | 2026-06-02 | 15000 | 0% | Not started
NV-20 | Train-the-trainer sessions (5 depts) | Omar Hassan | 2026-05-29 | 2026-06-03 | 12000 | 0% | Not started
NV-21 | End-user training rollout | Catherine Reyes | 2026-06-01 | 2026-06-04 | 18000 | 0%
PHASE 5: LAUNCH & HANDOVER
NV-22 | Phased go-live (dept by dept) | Leo Park | 2026-06-01 | 2026-06-04 | 20000 | 0% | Not started
NV-23 | Legacy system decommission | Leo Park | 2026-06-03 | 2026-06-05 | 10000 | 0% | Not started
NV-24 | Hypercare support & issue triage | All Team | 2026-06-01 | 2026-06-05 | 15000 | 0% | Not started
NV-25 | Project closure & lessons learned | Catherine Reyes | 2026-06-05 | 2026-06-05 | 2000 | 0% | Not started
Note: This is a free version of the template that allows you to manage up to 35 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Budget Tracker
💰 | BUDGET TRACKER
Linked to Project Plan tab — tracks planned vs actual spend per task
Task ID | Task Name | Planned Cost | Actual Cost | Variance | % Spent | Status | Notes
NV-01 | Current state assessment | 15000 | 15000 | 0 | 100% | Complete | Assessment delivered on time; vendor benchmarks attached.
NV-02 | Stakeholder interviews | 8000 | 7500 | 500 | 93.75% | Under budget | Saved $500 by combining sessions across departments.
NV-03 | Vendor evaluation | 5000 | 5200 | -200 | 104% | License negotiation | License count exceeded forecast by 4%; renegotiating tier.
NV-04 | Charter & roadmap | 2000 | 2000 | 0 | 100% | Complete | Charter signed by sponsor; baseline locked.
NV-05 | Infrastructure readiness | 12000 | 11800 | 200 | 98.33% | Complete | Network upgrade required minor scope add; absorbed in budget.
NV-06 | IA design | 18000 | 18000 | 0 | 100% | Complete | IA approved by stakeholders; no rework expected.
NV-07 | SharePoint structure | 15000 | 14500 | 500 | 96.67% | Complete | Permissions matrix took longer than planned but within budget.
NV-08 | Teams governance | 10000 | 4000 | 6000 | 40% | In progress | Governance policies pending IT security sign-off.
NV-09 | Power Platform prototypes | 20000 | 6000 | 14000 | 30% | In progress | 3 of 6 prototypes delivered; remaining flows in dev.
NV-10 | Branding & UX | 8000 | 2000 | 6000 | 25% | In progress | Branding kit shared with vendor; UX iterations ongoing.
NV-11 | Email migration | 25000 | 5000 | 20000 | 20% | In progress | Pilot complete for IT (50 users); full rollout next sprint.
NV-12 | Document migration | 22000 | 3000 | 19000 | 13.64% | In progress | Finance dept migration in progress; 30% complete.
NV-13 | Content migration | 18000 | 0 | 18000 | 0% | Not started | Awaiting content owner approvals before kickoff.
NV-14 | Power Automate flows | 15000 | 0 | 15000 | 0% | Not started | Dependencies on email migration; scheduled to start W6.
NV-15 | Custom app dev | 30000 | 0 | 30000 | 0% | Not started | RFP issued to 3 vendors; selection by month-end.
NV-16 | SSO & security | 12000 | 0 | 12000 | 0% | Not started | Architecture reviewed; awaiting AD integration window.
NV-17 | Integration testing | 8000 | 0 | 8000 | 0% | Not started | Test plans drafted; environment provisioning underway.
NV-18 | UAT | 5000 | 0 | 5000 | 0% | Not started | UAT scenarios drafted; pending business sign-off.
NV-19 | Training materials | 15000 | 0 | 15000 | 0% | Not started | Outline approved; storyboarding in progress.
NV-20 | Train-the-trainer | 12000 | 0 | 12000 | 0% | Not started | Trainer cohort identified; sessions scheduled W8.
NV-21 | End-user training | 18000 | 0 | 18000 | 0% | Not started | Awaiting training materials before scheduling.
NV-22 | Phased go-live | 20000 | 0 | 20000 | 0% | Not started | Phased plan drafted; cutover dates TBD.
NV-23 | Legacy decommission | 10000 | 0 | 10000 | 0% | Not started | Decommission checklist drafted; data archive in scope.
NV-24 | Hypercare support | 15000 | 0 | 15000 | 0% | Not started | Hypercare team assigned; SLAs being finalized.
NV-25 | Project closure | 2000 | 0 | 2000 | 0% | Not started | Closure checklist drafted; lessons-learned session planned.
TOTALS |  | 340000 | 94000 | 246000 | 27.65%

## Risk Register
⚠️ | RISK REGISTER
Identify, assess, and track project risks with mitigation strategies
Risk ID | Risk Description | Probability | Impact | Score | Mitigation Strategy | Owner | Status
R-01 | Data loss during migration | High | High | 9 | Full backup before each migration wave, parallel run for 2 weeks | Leo Park | Open
R-02 | User resistance to new tools | Medium | High | 6 | Early champion program, lunch-and-learn sessions, quick wins first | Omar Hassan | Closed
R-03 | Budget overrun on custom dev | Medium | Medium | 4 | Cap custom dev at $30K, use out-of-box features where possible | Catherine Reyes | Open
R-04 | Integration failures with legacy | High | Medium | 6 | Build integration test suite early, maintain legacy bridge for 30 days | Leo Park | Mitigating
R-05 | Vendor licensing cost increase | Low | High | 3 | Lock 3-year pricing in contract, negotiate enterprise agreement | Catherine Reyes | Watching
R-06 | Key staff turnover mid-project | Low | Medium | 2 | Cross-train team members, document all configurations | Catherine Reyes | Watching
R-07 | SharePoint performance issues | Medium | Medium | 4 | Performance testing at 50% migration, CDN for media files | Leo Park | Open
R-08 | Training schedule conflicts | Medium | Low | 2 | Offer multiple time slots, record all sessions for async viewing | Omar Hassan | Open

## RACI Matrix
👥 | RACI MATRIX
R=Responsible, A=Accountable, C=Consulted, I=Informed
Task ID | Task / Deliverable | Catherine Reyes | Omar Hassan | Leo Park | Mei Zhang | Sponsor
NV-01 | Current state assessment | A | C | R | C | I
NV-02 | Stakeholder interviews | A | R | C | C | I
NV-03 | Vendor evaluation | R | C | C | I | A
NV-06 | IA design | A | C | I | R | I
NV-07 | SharePoint structure | C | I | R | C | I
NV-08 | Teams governance | A | R | C | I | I
NV-09 | Power Platform prototypes | C | I | I | R | I
NV-11 | Email migration | I | I | R | C | I
NV-12 | Document migration | I | C | R | I | I
NV-13 | Content migration | C | R | I | C | I
NV-15 | Custom app dev | R | I | C | R | I
NV-17 | Integration testing | A | C | R | C | I
NV-19 | Training materials | R | C | I | C | A
NV-20 | Train-the-trainer | C | R | I | C | I
NV-22 | Phased go-live | A | C | R | C | I
NV-25 | Project closure | R | C | C | C | A

## Dashboard
| PROJECT DASHBOARD |  | #04 All-in-One Project Planner
Auto-populated from Project Plan and Budget tabs
KEY METRICS
Overall Progress |  | 41% | Schedule Status | On Track | Budget Health | 77% remaining
Tasks Completed |  | 7 of 25 | Tasks In Progress | 10 | Tasks Not Started | 8
Budget Planned |  | 410000 | Budget Spent | 94000 | Budget Variance | 316000
Open Risks |  | 5 | High Risks | 2 | Days Remaining | 25
STATUS BREAKDOWN |  |  |  |  | RISK BREAKDOWN
| Status | Count |  |  | Severity | Count
✅ | Completed | 7 |  |  | High (≥6) | 2
🔄 | In Progress | 10 |  |  | Medium (3-5) | 3
⏳ | Not Started | 8 |  |  | Low (<3) | 2
BUDGET BY PHASE
| Phase | Planned | Actual
🏁 | Assessment | 42000 | 42000
🏁 | Design | 71000 | 44500
🏁 | Migration | 122000 | 8000
🏁 | Testing | 58000 | 0
🏁 | Launch | 47000 | 0
PROJECT GOVERNANCE SUMMARY
📅 Milestones Complete |  | 7 of 12 | ⚠️ Open Issues | 5 | 🔄 Pending CRs | 3
✔️ Open Actions |  | 8 | 📜 Charter Approvals | 4 approved | 👥 Stakeholders Tracked | 8
🧭 Decisions Logged |  | 8 | 💡 Lessons Captured | 4 | 🚨 High Risks Open | 2
RESOURCES & SCHEDULE
👷 Resources Allocated |  | 8 | 💰 Total Resource Cost | 259679.5714 | ⏱ Total Hours Planned | 1586.6286
📣 Comm. Channels |  | 12 | 📅 Milestones Total | 12 | ⏰ Overdue Actions | 0

## Instructions
📘 How to Use This All-in-One Project Planner
A single workbook to plan, run, and close out a project — schedule, budget, risks, governance, and reporting all linked together.
🚀 QUICK START
1. Build the schedule on Project Plan — list tasks, owners, dates, budgets, and progress %.
2. Track planned vs actual spend per task in Budget Tracker.
3. Identify and score risks in Risk Register; review weekly.
4. Clarify ownership per task in RACI Matrix.
5. Review Dashboard for at-a-glance project health.
💎 Want more? The full version adds Project Charter, Milestones, Stakeholder Register, Communication Plan, Resource Plan, Status Report, Action Items, Issue Log, Decision Log, Change Request Log, and Lessons Learned.
🗂️ SHEET-BY-SHEET GUIDE
Sheet | Purpose | When to Use | Key Fields to Fill
📈 Dashboard | Auto-rolled metrics across the workbook for at-a-glance project health. | Read-only — review before status meetings. | No input needed; values reference other sheets.
📅 Project Plan | Master schedule with WBS, owners, dates, budget, progress %, status, and a visual Gantt. | Daily — your project's main working tab. | WBS, Phase/Task, Assigned To, Planned Start/End, Budget, Progress (0–1), Status.
💰 Budget Tracker | Planned vs actual cost per task with variance and % spent. | Update weekly as actuals come in. | Task ID, Planned Cost, Actual Cost, Status, Notes. Variance and % Spent are formula-driven.
⚠️ Risk Register | Identify potential risks, score them, and track mitigation. | Review weekly — risks evolve. | Risk Description, Probability, Impact, Score (P×I), Mitigation, Owner, Status.
👥 RACI Matrix | Clarify Responsible / Accountable / Consulted / Informed per task. | After task list is stable; revisit if owners change. | Task ID, Task, then R/A/C/I letter per team member column.
🔗 HOW THE SHEETS LINK TOGETHER
• Task IDs (e.g. NV-01) on Project Plan are the spine — they reappear in Budget Tracker and RACI Matrix.
• Budget Tracker rolls up planned/actual spend that feeds Dashboard's budget tiles.
• Risk Register feeds the risk tiles on Dashboard — keep statuses and scores current.
• Dashboard summarizes everything else — keep upstream sheets current and the dashboard stays accurate.
✅ STATUS & SCORING CONVENTIONS
Label | Meaning
Completed | Work delivered and accepted; Progress = 100%.
In Progress | Actively being worked; Progress between 0% and 100%.
Not Started | Scheduled but no work begun; Progress = 0%.
Risk Score | Probability × Impact. High ≥ 6, Medium 3–5, Low < 3.
💡 TIPS
• Enter Progress as a decimal (0.5 = 50%) — the cell is formatted as %.
• Keep Task IDs consistent across Project Plan, Budget Tracker, and RACI Matrix so links don't break.
• Update actuals in Budget Tracker weekly — Variance and % Spent are formula-driven.
• Re-score risks each week and update Status as mitigation progresses.
• Don't edit Dashboard cells directly; fix the source sheet instead.

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms

## Analysistabs
1
DO NOT DELETE OR MODIFY THIS SHEET
WARNING — SYSTEM SHEET
This sheet is required for the template to function correctly.
It contains essential configuration used by formulas, conditional formatting,
Gantt chart rendering, progress bars, and KPI calculations.
| If this sheet is deleted or modified: | 1
| • Gantt chart bars will stop rendering | 1
| • Progress bars will show errors | 1
• KPI cards will display #REF! errors
• Conditional formatting will break
• Auto-calculated fields will stop working
This sheet will be hidden when the template is exported.
Users will not see this sheet in the downloaded file.
Analysistabs® ¦ Excelx.com ¦ Template Configuration Sheet