## 7 Construction
| Construction Project Planner | [8 empty] | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | IN PROGRESS | [6 empty] | NOT STARTED | [6 empty] | 🎢 Overall Progress |  |  | 21.43% |  |  | 0.21429 | Phase 1 |  |  |  |  | Phase 2 |  |  |  |  | Phase 3 |  |  |  |  | Phase 4 |  |  |  |  | Phase 5 |  |  |  |  | Phase 6 |  |  |  |  | Phase 7
| Residential Build: 10 weeks construction schedule | [8 empty] | 35 | [6 empty] | 6 | [6 empty] | 3 | [6 empty] | 26 | [13 empty] | Completed |  |  |  |  | In progress |  |  |  |  | Not started |  |  |  |  | Not started |  |  |  |  | Not started |  |  |  |  | Not started |  |  |  |  | Not started
| Oakwood Heights — 3BR Residential Build | [42 empty] | 0.78571
Project Details | Project Name | Oakwood Heights — 3BR Residential Build |  |  | Site Address | 742 Oakwood Dr, San Jose, CA |  | Start Date | 2026-05-04 | 🎯 Project Objective | [6 empty] | Accelerate the deployment of core infrastructure while simultaneously executing a high-impact marketing and beta-testing sequence to ensure a 100% stable production release.
| Project Manager | David Martinez | [5 empty] | End Date | 2026-07-12 | [59 empty] | Completed | 6
| General Contractor | Martinez Construction LLC | Created On | 2026-04-20 | Project Value | 580000 |  | Duration | 70 | [59 empty] | In progress | 3
| Created By | David Martinez | Last Updated | 2026-04-20 | Permit # | BLD-2026-08471 |  | Days Left | 65 | [59 empty] | Not started | 26
Task Table | [9 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24 | [6 empty] | WEEK 25 | [6 empty] | WEEK 26 | [6 empty] | WEEK 27 | [6 empty] | WEEK 28
[10 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Phase/Task Name | Subcontractor | Materials | Permit # | Assigned To | Start Date | End Date | Progress | Status | time axis 2026-05-04 to 2026-07-12
PHASE 1: SITE PREPARATION & PERMITS
CS-01 | Submit building permit application | — | — | BLD-2026-0847 | David Martinez | 2026-05-04 | 2026-05-08 | 100% | Completed
CS-02 | Site survey & soil testing | Bay Area Geo LLC | — | GEO-2026-112 | David Martinez | 2026-05-04 | 2026-05-07 | 100% | Completed
CS-03 | Utility locate & mark-out | PG&E / Water District | Marking paint | — | David Martinez | 2026-05-06 | 2026-05-08 | 100% | Completed
CS-04 | Demolition & site clearing | Pacific Demo Co | Dumpster rental | DEM-2026-045 | Tony Reeves | 2026-05-07 | 2026-05-13 | 100% | Completed
CS-05 | Rough grading & compaction | Martinez Excavation | Gravel, fill dirt | — | Tony Reeves | 2026-05-11 | 2026-05-15 | 100% | Completed
PHASE 2: FOUNDATION
CS-06 | Excavation for footings | Martinez Excavation | — | — | Tony Reeves | 2026-05-14 | 2026-05-18 | 100% | Completed
CS-07 | Form & pour concrete footings | Summit Concrete Inc | Concrete 4000PSI, rebar | — | Carlos Vega | 2026-05-18 | 2026-05-22 | 80% | In progress
CS-08 | Foundation wall pour | Summit Concrete Inc | Concrete, anchor bolts | — | Carlos Vega | 2026-05-21 | 2026-05-27 | 50% | In progress
CS-09 | Foundation waterproofing | WaterShield Pros | Membrane, drain tile | — | Carlos Vega | 2026-05-26 | 2026-05-29 | 20% | In progress
CS-10 | Foundation inspection | Bay Area Inspections | — | INS-2026-201 | David Martinez | 2026-05-29 | 2026-05-29 | 0% | Not started
PHASE 3: FRAMING & STRUCTURE
CS-11 | Sill plate & floor framing | Johnson Framing LLC | Lumber, sill seal | — | Mike Johnson | 2026-06-01 | 2026-06-05 | 0% | Not started
CS-12 | Wall framing — ext & int | Johnson Framing LLC | 2x4 studs, headers | — | Mike Johnson | 2026-06-04 | 2026-06-12 | 0% | Not started
CS-13 | Roof truss installation | Johnson Framing LLC | Pre-fab trusses | — | Mike Johnson | 2026-06-11 | 2026-06-16 | 0% | Not started
CS-14 | Roof sheathing & felt paper | Johnson Framing LLC | OSB, roofing felt | — | Mike Johnson | 2026-06-15 | 2026-06-18 | 0% | Not started
CS-15 | Framing inspection | Bay Area Inspections | — | INS-2026-202 | David Martinez | 2026-06-19 | 2026-06-19 | 0% | Not started
PHASE 4: MEP ROUGH-IN
CS-16 | Rough plumbing | Summit Plumbing Co | PVC, copper, fittings | — | Ray Delgado | 2026-06-11 | 2026-06-17 | 0% | Not started
CS-17 | Electrical rough-in & panel | Martinez Electric LLC | Romex, panel, boxes | ELE-2026-318 | Luis Martinez | 2026-06-11 | 2026-06-18 | 0% | Not started
CS-18 | HVAC ductwork & unit set | CoolAir Systems | Ductwork, registers | MEC-2026-044 | Pete Sandoval | 2026-06-14 | 2026-06-19 | 0% | Not started
CS-19 | MEP inspection | Bay Area Inspections | — | INS-2026-203 | David Martinez | 2026-06-21 | 2026-06-21 | 0% | Not started
PHASE 5: EXTERIOR & INSULATION
CS-20 | Window & door install | Valley Glass & Door | Windows, entry door | — | Carlos Vega | 2026-06-17 | 2026-06-22 | 0% | Not started
CS-21 | Roofing shingles & flashing | Premier Roofing Inc | Arch. shingles | — | James Kwan | 2026-06-14 | 2026-06-19 | 0% | Not started
CS-22 | Siding & exterior trim | Westcoast Exteriors | Hardie board, trim | — | Carlos Vega | 2026-06-21 | 2026-06-28 | 0% | Not started
CS-23 | Insulation — walls & attic | EcoInsulate Co | Batt & blown-in | INS-2026-090 | Tony Reeves | 2026-06-22 | 2026-06-25 | 0% | Not started
CS-24 | Insulation inspection | Bay Area Inspections | — | INS-2026-204 | David Martinez | 2026-06-28 | 2026-06-28 | 0% | Not started
PHASE 6: INTERIOR FINISHES
CS-25 | Drywall hang, tape & texture | Pacific Drywall | Drywall, mud, tape | — | Tony Reeves | 2026-06-21 | 2026-06-28 | 0% | Not started
CS-26 | Interior paint | Fresh Coat Painting | Primer, paint, caulk | — | Tony Reeves | 2026-06-28 | 2026-07-02 | 0% | Not started
CS-27 | Flooring — tile & hardwood | Precision Floors Inc | Tile, hardwood | — | Carlos Vega | 2026-06-29 | 2026-07-05 | 0% | Not started
CS-28 | Cabinet & countertop install | Custom Cabinets Plus | Cabinets, quartz | — | Carlos Vega | 2026-07-01 | 2026-07-06 | 0% | Not started
CS-29 | Plumbing & elec trim-out | Summit / Martinez Elec | Fixtures, outlets | — | Ray Delgado | 2026-07-05 | 2026-07-08 | 0% | Not started
PHASE 7: FINAL & CLOSEOUT
CS-30 | Final cleaning & touch-ups | CleanBuild Services | Cleaning supplies | — | Tony Reeves | 2026-07-07 | 2026-07-08 | 0% | Not started
CS-31 | Final building inspection | Bay Area Inspections | — | INS-2026-205 | David Martinez | 2026-07-09 | 2026-07-09 | 0% | Not started
CS-32 | Punch list walkthrough | — | — | — | David Martinez | 2026-07-09 | 2026-07-10 | 0% | Not started
CS-33 | Punch list corrections | All trades | Misc. materials | — | David Martinez | 2026-07-10 | 2026-07-11 | 0% | Not started
CS-34 | Certificate of Occupancy | City of San Jose | — | CO-2026-FINAL | David Martinez | 2026-07-11 | 2026-07-11 | 0% | Not started
CS-35 | Client handover & warranty | — | Warranty binder | — | David Martinez | 2026-07-12 | 2026-07-12 | 0% | Not started
Note: This is a free version of the template that allows you to manage up to 35 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Blank Template
| Construction Project Planner | [8 empty] | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | IN PROGRESS | [6 empty] | NOT STARTED | [6 empty] | 🎢 Overall Progress |  |  | 0% |  |  | 0 | Phase 1 |  |  |  |  | Phase 2 |  |  |  |  | Phase 3 |  |  |  |  | Phase 4 |  |  |  |  | Phase 5 |  |  |  |  | Phase 6 |  |  |  |  | Phase 7
| Residential Build: 10 weeks construction schedule | [8 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [13 empty] | Completed |  |  |  |  | In progress |  |  |  |  | Not started |  |  |  |  | Not started |  |  |  |  | Not started |  |  |  |  | Not started |  |  |  |  | Not started
1
Project Details | Project Name |  |  |  | Site Address |  |  | Start Date |  | 🎯 Project Objective
| Project Manager | [6 empty] | End Date | [60 empty] | Completed | 0
| General Contractor |  | Created On |  | Project Value |  |  | Duration | [60 empty] | In progress | 0
| Created By |  | Last Updated |  | Permit # |  |  | Days Left | [60 empty] | Not started | 0
Task Table | [9 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24 | [6 empty] | WEEK 25 | [6 empty] | WEEK 26 | [6 empty] | WEEK 27 | [6 empty] | WEEK 28
[10 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Phase/Task Name | Subcontractor | Materials | Permit # | Assigned To | Start Date | End Date | Progress | Status | time axis 2026-05-04 to 2026-07-12
Note: This is a free version of the template that allows you to manage up to 35 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Instructions
Construction Project Planner - Instructions
FIELD | WHAT TO ENTER
Project Name | Enter your project name (e.g., Website Redesign, ERP Migration).
Project Manager | Name of the person managing this project.
General Contractor | General contractor company name.
Start Date | Auto-calculated. Do not edit (grey cell).
End Date | Auto-calculated. Do not edit (grey cell).
Duration | Auto-calculated. Do not edit (grey cell).
Days Left | Auto-calculated. Do not edit (grey cell).
Project Value | Total project budget (e.g., $150,000).
Site Address | Construction site address.
Permit # | Building permit number.
🎯 Project Objective | 1-2 sentence project goal and measurable success criteria.
Created By | Name of the person who created this plan.
Created On | Date this plan was created (MM/DD/YYYY).
Last Updated | Date of last update (MM/DD/YYYY).
Completed | Auto-calculated. Do not edit (grey cell).
6 | Enter the 6 value.
In progress | Auto-calculated. Do not edit (grey cell).
3 | Enter the 3 value.
Not started | Auto-calculated. Do not edit (grey cell).
26 | Enter the 26 value.
Task Table Columns
ID | Unique task identifier (e.g., WF-01). Keep sequential.
Phase/Task Name | Clear, action-oriented task description.
Subcontractor | Subcontractor company name.
Materials | Required materials for this task.
Permit # | Permit number if required.
Assigned To | Team member responsible for this task.
Start Date | Task start date (MM/DD/YYYY).
End Date | Task end date (MM/DD/YYYY).
Progress | Enter manually (0% to 100%). Update daily.
Status | Auto-calculated. Do not edit.
Gantt Chart | Auto-generated from Start/End dates. Do not edit. Bars update automatically.
Grey / Locked Cells
Light grey cells | Contain formulas - auto-calculated from your entries.
Formula bar blank | By design - formulas are hidden for protection.
Cannot edit | These cells are locked. Only white cells are editable.
Tips
Phase rows | Bold colored rows are section headers. Enter tasks below them.
Dropdowns | Click cells with small arrows to see available options.
Dates | Use MM/DD/YYYY format for all date fields.
Progress | Enter manually (0% to 100%). Update daily as work progresses.
Status | Auto-calculated from Progress. 100%=Completed, 1-99%=In progress, 0%=Not started.
Save often | File > Save As to create backup versions.
Need More Features?
More tasks | FREE version supports 25 tasks. Premium = unlimited tasks with auto-expanding rows.
Longer Gantt | FREE = 5-week Gantt. Premium = 9-week dynamic view with zoom in/out.
Unlimited Projects | Premium supports unlimited project sheets with one-click duplication.
Fully Unlocked | All cells editable. No locked sheets, no hidden formulas, no restrictions.
Fully Customizable | Easily customize colors, layout, and fields to suit any project type or industry.
Get Premium Template | Visit analysistabs.org/product/simple-multiple-project-tracking-template-excel/
Excel PM Templates by PNRao ¦ Excelx.com ¦ Powered by Analysistabs®

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms

## Analysistabs (hidden)
1
DO NOT DELETE OR MODIFY THIS SHEET
WARNING — SYSTEM SHEET
This sheet is required for the template to function correctly.
It contains essential configuration used by formulas, conditional formatting,
Gantt chart rendering, progress bars, and KPI calculations.
| If this sheet is deleted or modified: | 1
| • Gantt chart bars will stop rendering | 1
| • Progress bars will show errors | 1
• KPI cards will display #REF! errors
• Conditional formatting will break
• Auto-calculated fields will stop working
This sheet will be hidden when the template is exported.
Users will not see this sheet in the downloaded file.
Analysistabs® ¦ Excelx.com ¦ Template Configuration Sheet