## 18 Event Planning
| Event Planning Project Plan | [7 empty] | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | VENDORS BOOKED | [6 empty] | DAYS TO EVENT | [6 empty] | 🎢 Overall Progress |  |  | 43% |  |  | 0.43
| Event Roadmap: 5-week conference planning & execution | [7 empty] | 25 | [6 empty] | 7 | [6 empty] | 6 | [6 empty] | 28
| Innovate 2026: Annual Customer Conference | [41 empty] | 0.57
Project Details | Project Name | Innovate 2026: Annual Customer Conference |  |  | Event Date | 2026-06-05 | Venue | Grand Hyatt Ballroom, San Jose | 🎯 Project Objective | [6 empty] | Plan and execute a 350-person customer conference with 3 keynotes, 8 breakout sessions, sponsor expo, and networking reception. Achieve 90% attendee satisfaction, 40+ qualified leads for sales, and full social media coverage.
| Event Manager | Sophia Tran |  |  | Event Time | 9:00 AM — 5:00 PM | Event Type | Full-day conference + networking | [29 empty] | Completed | 7
| Department | Events & Marketing | Created On | 2026-04-20 | Total Budget | $92,000 | Registrations | 287 of 350 (82%) | [29 empty] | In progress | 6
| Created By | Sophia Tran | Last Updated | 2026-04-20 | Expected Attendees | 350 guests | Sponsors Confirmed | 4 (Gold: 2, Silver: 2) | [29 empty] | Not started | 12
Task Table | [8 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Task Name | Vendor | Venue/Location | Assigned To | Start Date | End Date | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
PHASE 1: PLANNING & BOOKINGS
EV-01 | Confirm venue contract & floor plan | Grand Hyatt | Ballroom A+B | Sophia Tran | 2026-05-04 | 2026-05-06 | 100% | Completed
EV-02 | Book keynote speakers (3 confirmed) | Speaker Bureau | Main Stage | Sophia Tran | 2026-05-04 | 2026-05-08 | 100% | Completed
EV-03 | Select & contract catering vendor | Bay Catering Co | Kitchen/Hall | Jake Russo | 2026-05-05 | 2026-05-09 | 100% | Completed
EV-04 | Book AV & production company | ProSound Events | All Rooms | Maya Singh | 2026-05-05 | 2026-05-08 | 100% | Completed
EV-05 | Secure event photographer & videographer | Lens Creative | All Rooms | Maya Singh | 2026-05-06 | 2026-05-09 | 100% | Completed
EV-06 | Finalize sponsor packages & agreements | — | Expo Hall | Sophia Tran | 2026-05-07 | 2026-05-12 |  | Not started
EV-07 | Launch registration page (Eventbrite) | Eventbrite | Online | Jake Russo | 2026-05-08 | 2026-05-09 | 100% | Completed
| PHASE 2: CONTENT & PROMOTION | [5 empty] | 100%
EV-08 | Finalize session agenda & speaker schedule | — | All Rooms | Sophia Tran | 2026-05-11 | 2026-05-15 | 80% | In progress
EV-09 | Design event branding (logo, signage) | DesignWorks | All Rooms | Maya Singh | 2026-05-12 | 2026-05-16 | 60% | In progress
EV-10 | Email campaign — 3 invite waves | — | Online | Jake Russo | 2026-05-12 | 2026-05-22 | 100% | Completed
EV-11 | Social media promotion (4-week plan) | — | Online | Maya Singh | 2026-05-12 | 2026-05-29 |  | Not started
EV-12 | Prepare speaker presentation templates | — | — | Jake Russo | 2026-05-14 | 2026-05-19 | 50% | In progress
EV-13 | Print name badges, programs & signage | FastPrint Co | — | Maya Singh | 2026-05-18 | 2026-05-23 | 40% | In progress
| PHASE 3: LOGISTICS & SETUP | [5 empty] | 20%
EV-14 | Confirm final catering menu & headcount | Bay Catering Co | Kitchen | Jake Russo | 2026-05-20 | 2026-05-23 | 15% | In progress
EV-15 | Coordinate sponsor booth assignments | — | Expo Hall | Sophia Tran | 2026-05-21 | 2026-05-26 | 10% | In progress
EV-16 | Prepare attendee swag bags (350 units) | SwagBox Inc | Storage Room | Maya Singh | 2026-05-22 | 2026-05-28 | 0% | Not started
EV-17 | Brief volunteers & assign stations (12) | — | All Rooms | Jake Russo | 2026-05-26 | 2026-05-29 |  | Not started
EV-18 | AV tech rehearsal & sound check | ProSound Events | Main Stage | Maya Singh | 2026-06-02 | 2026-06-03 | 0% | Not started
EV-19 | Venue walkthrough & final setup | Grand Hyatt | All Rooms | Sophia Tran | 2026-06-03 | 2026-06-03 | 0% | Not started
| PHASE 4: EVENT DAY | [5 empty] | 0%
EV-20 | Registration desk & check-in (7:30 AM) | — | Lobby | Jake Russo | 2026-06-04 | 2026-06-04 | 0% | Not started
EV-21 | Keynotes + breakout sessions (9AM-4PM) | — | All Rooms | Sophia Tran | 2026-06-04 | 2026-06-04 | 0% | Not started
EV-22 | Networking reception & sponsor expo (4-6PM) | Bay Catering Co | Expo Hall | Jake Russo | 2026-06-04 | 2026-06-04 |  | Not started
| PHASE 5: POST-EVENT | [5 empty] | 0%
EV-23 | Send attendee thank-you email + survey | — | Online | Jake Russo | 2026-06-04 | 2026-06-05 | 0% | Not started
EV-24 | Collect & share event photos/video | Lens Creative | Online | Maya Singh | 2026-06-04 | 2026-06-05 | 0% | Not started
EV-25 | Post-event report & ROI analysis | — | — | Sophia Tran | 2026-06-05 | 2026-06-05 | 0% | Not started
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Blank Template
| Event Planning Project Plan | [7 empty] | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | VENDORS BOOKED | [6 empty] | DAYS TO EVENT | [6 empty] | 🎢 Overall Progress |  |  | 0% |  |  | 0
| Event Roadmap: 5-week conference planning & execution | [7 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
1
Project Details | Project Name |  |  |  | Event Date |  | Venue |  | 🎯 Project Objective
| Event Manager |  |  |  | Event Time |  | Event Type | [30 empty] | Completed | 0
| Department |  | Created On |  | Total Budget |  | Registrations | [30 empty] | In progress | 0
| Created By |  | Last Updated |  | Expected Attendees |  | Sponsors Confirmed | [30 empty] | Not started | 0
Task Table | [8 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Task Name | Vendor | Venue/Location | Assigned To | Start Date | End Date | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Instructions
Event Planning Project Plan - Instructions
FIELD | WHAT TO ENTER
Project Name | Enter your project name (e.g., Website Redesign, ERP Migration).
Event Manager | Name of the person managing this project.
Department | Your department or client name.
Event Date | Auto-calculated. Do not edit (grey cell).
Event Time | Event start time.
Total Budget | Total project budget (e.g., $150,000).
Sponsors Confirmed | Executive sponsor name and title.
Venue | Event venue name and address.
Event Type | Type of event (Conference, Workshop, etc.).
Expected Attendees | Expected number of attendees.
Registrations | Current registration count.
🎯 Project Objective | 1-2 sentence project goal and measurable success criteria.
Created By | Name of the person who created this plan.
Created On | Date this plan was created (MM/DD/YYYY).
Last Updated | Date of last update (MM/DD/YYYY).
Task Table Columns
ID | Unique task identifier (e.g., WF-01). Keep sequential.
Task Name | Clear, action-oriented task description.
Vendor | Vendor or supplier name.
Venue/Location | Venue or location for this task.
Assigned To | Team member responsible for this task.
Start Date | Task start date (MM/DD/YYYY).
End Date | Task end date (MM/DD/YYYY).
Progress | Enter manually (0% to 100%). Update daily.
Status | Auto-calculated. Do not edit.
Gantt Chart | Auto-generated from Start/End dates. Do not edit. Bars update automatically.
Grey / Locked Cells
Light grey cells | Contain formulas - auto-calculated from your entries.
Formula bar blank | By design - formulas are hidden for protection.
Cannot edit | These cells are locked. Only white cells are editable.
Tips
Phase rows | Bold colored rows are section headers. Enter tasks below them.
Dropdowns | Click cells with small arrows to see available options.
Dates | Use MM/DD/YYYY format for all date fields.
Progress | Enter manually (0% to 100%). Update daily as work progresses.
Status | Auto-calculated from Progress. 100%=Completed, 1-99%=In progress, 0%=Not started.
Save often | File > Save As to create backup versions.
Need More Features?
More tasks | FREE version supports 25 tasks. Premium = unlimited tasks with auto-expanding rows.
Longer Gantt | FREE = 5-week Gantt. Premium = 9-week dynamic view with zoom in/out.
Unlimited Projects | Premium supports unlimited project sheets with one-click duplication.
Fully Unlocked | All cells editable. No locked sheets, no hidden formulas, no restrictions.
Fully Customizable | Easily customize colors, layout, and fields to suit any project type or industry.
Get Premium Template | Visit analysistabs.org/product/simple-multiple-project-tracking-template-excel/
Excel PM Templates by PNRao ¦ Excelx.com ¦ Powered by Analysistabs®

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms

## Analysistabs (hidden)
1
DO NOT DELETE OR MODIFY THIS SHEET
WARNING — SYSTEM SHEET
This sheet is required for the template to function correctly.
It contains essential configuration used by formulas, conditional formatting,
Gantt chart rendering, progress bars, and KPI calculations.
| If this sheet is deleted or modified: | 1
| • Gantt chart bars will stop rendering | 1
| • Progress bars will show errors | 1
• KPI cards will display #REF! errors
• Conditional formatting will break
• Auto-calculated fields will stop working
This sheet will be hidden when the template is exported.
Users will not see this sheet in the downloaded file.
Analysistabs® ¦ Excelx.com ¦ Template Configuration Sheet