## 13 Multi-Project
| Multi-Project Portfolio Planner | [10 empty] | TOTAL PROJECTS | [6 empty] | ON TRACK | [6 empty] | AT RISK | [6 empty] | OFF TRACK | [6 empty] | 🎢 Overall Progress |  |  | 29.6% |  |  | 0.296
| Portfolio Dashboard: Track 10 projects across departments on one page | [10 empty] | 25 | [6 empty] | 15 | [6 empty] | 8 | [6 empty] | 2
| FY2026 Q3 — Digital Transformation | [44 empty] | 0.704
Project Details | Portfolio Name | FY2026 Q3 — Digital Transformation |  |  |  | Reporting Period | Q3 2026 (May-Jul) |  | Active Projects | 25 |  | 🎯 Project Objective | [6 empty] | Deliver 25 digital transformation initiatives spanning IT, Infrastructure, Marketing, HR, Finance, and Operations by end of FY2026. Each project has an independent PM but reports into a unified portfolio dashboard for executive visibility.
| Portfolio Director | Amanda Chen |  |  |  | Total Budget | 5510000 |  | Completed | 3 | [30 empty] | Completed | 2
| PMO Lead | Robert Kimura | Created On | 2026-05-04 |  | Next Review | May 30, 2026 (Steering) |  | Avg Progress | 29.6% | [30 empty] | In progress | 13
| Created By | Robert Kimura | Last Updated | 2026-05-04 |  | Portfolio Health | Red — Critical issues |  | Budget Utilized | 38.28% | [30 empty] | Not started | 9
Project Portfolio | [11 empty] | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28
ID | Project Name | Project Manager | Department | Priority | Budget | RAG | Current Phase | Start Date | End Date | Progress | Status
PRJ-01 | Cloud ERP Implementation | Nathan Brooks | Enterprise IT | High | 485000 | Green | Execution | 2026-05-05 | 2026-07-07 | 100% | Completed
PRJ-02 | Customer Self-Service Portal | Catherine Reyes | Digital Products | High | 340000 | Green | Design | 2026-05-12 | 2026-08-11 | 100% | Completed
PRJ-03 | Data Center Migration | Sarah Kim | Infrastructure | High | 275000 | Green | Migration | 2026-05-05 | 2026-06-23 | 100% | Completed
PRJ-04 | Marketing Automation Platform | Jessica Morales | Marketing | Medium | 180000 | Amber | Build | 2026-05-26 | 2026-08-04 | 65% | In progress
PRJ-05 | HR System Consolidation | Monica Alvarez | HR | Medium | 290000 | Green | Execution | 2026-05-19 | 2026-07-21 | 35% | In progress
PRJ-06 | Mobile App v2.0 | Derek Huang | Product | High | 220000 | Amber | Sprint 3 | 2026-06-02 | 2026-08-25 | 40% | In progress
PRJ-07 | Office Relocation (Floor 3) | Jake Morrison | Facilities | Low | 95000 | Amber | Planning | 2026-06-16 | 2026-08-11 | 15% | In progress
PRJ-08 | Cybersecurity Hardening | Anna Kowalski | InfoSec | High | 150000 | Green | Testing | 2026-05-05 | 2026-06-30 | 60% | In progress
PRJ-09 | Vendor Portal Redesign | Yuki Tanaka | Procurement | Medium | 125000 | Red | Requirements | 2026-06-23 | 2026-09-15 | 10% | In progress
PRJ-10 | Employee Learning Platform | Nina Patel | L&D | Low | 195000 | Green | Initiation | 2026-07-14 | 2026-10-13 | 10% | In progress
PRJ-11 | Network Infrastructure Upgrade | Robert Chen | Infrastructure | High | 320000 | Green | Execution | 2026-05-19 | 2026-08-25 | 50% | In progress
PRJ-12 | Sales CRM Integration | Maria Gonzalez | Sales Ops | Medium | 210000 | Amber | Build | 2026-06-09 | 2026-09-01 | 35% | In progress
PRJ-13 | Procurement Workflow Automation | David Park | Procurement | Medium | 140000 | Green | Design | 2026-06-30 | 2026-09-15 | 30% | In progress
PRJ-14 | Warehouse Robotics Pilot | Lisa Thompson | Operations | High | 425000 | Amber | Pilot | 2026-05-26 | 2026-09-29 | 30% | In progress
PRJ-15 | Finance Reporting Modernization | Daniel Foster | Finance | High | 265000 | Green | Build | 2026-05-12 | 2026-07-21 | 50% | In progress
PRJ-16 | Customer Data Platform | Rachel Adams | Marketing | High | 310000 | Red | Requirements | 2026-07-07 | 2026-10-27 | 10% | In progress
PRJ-17 | Compliance Audit Remediation | Steven Wright | Compliance | High | 95000 | Amber | Execution | 2026-05-05 | 2026-07-14 | 0% | Not started
PRJ-18 | Legacy App Decommissioning | Andrew Mitchell | Enterprise IT | Low | 75000 | Green | Planning | 2026-08-11 | 2026-11-03 | 0% | Not started
PRJ-19 | Brand Refresh & Website | Olivia Bennett | Marketing | Medium | 185000 | Green | Design | 2026-06-16 | 2026-09-01 | 0% | Not started
PRJ-20 | Field Service Mobile Tools | Kevin Rodriguez | Field Ops | Medium | 160000 | Amber | Build | 2026-06-02 | 2026-09-01 | 0% | Not started
PRJ-21 | Identity & Access Management | Patricia Hayes | InfoSec | High | 245000 | Green | Execution | 2026-05-05 | 2026-08-04 | 0% | Not started
PRJ-22 | Supplier Risk Dashboard | James Coleman | Procurement | Low | 60000 | Green | Initiation | 2026-09-01 | 2026-11-24 | 0% | Not started
PRJ-23 | Onboarding Experience Redesign | Hannah Carter | HR | Medium | 110000 | Green | Design | 2026-06-23 | 2026-08-25 | 0% | Not started
PRJ-24 | BI & Analytics Platform Refresh | Christopher Lee | Data & Analytics | High | 385000 | Amber | Build | 2026-05-05 | 2026-09-15 | 0% | Not started
PRJ-25 | Disaster Recovery & BCP Refresh | Megan Sullivan | Infrastructure | High | 170000 | Green | Testing | 2026-05-12 | 2026-07-21 | 0% | Not started
Note: This is a free version of the template that allows you to manage up to 20 projects and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Blank Template
| Multi-Project Portfolio Planner | [10 empty] | TOTAL PROJECTS | [6 empty] | ON TRACK | [6 empty] | AT RISK | [6 empty] | OFF TRACK | [6 empty] | 🎢 Overall Progress |  |  | 0% |  |  | 0
| Portfolio Dashboard: Track 10 projects across departments on one page | [10 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
1
Project Details | Portfolio Name |  |  |  |  | Reporting Period |  |  | Active Projects | 0 |  | 🎯 Project Objective
| Portfolio Director |  |  |  |  | Total Budget | 0 |  | Completed | 0 | [30 empty] | Completed | 0
| PMO Lead |  | Created On |  |  | Next Review |  |  | Avg Progress | [31 empty] | In progress | 0
| Created By |  | Last Updated |  |  | Portfolio Health |  |  | Budget Utilized | 0% | [30 empty] | Not started | 0
Project Portfolio | [11 empty] | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28
ID | Project Name | Project Manager | Department | Priority | Budget | RAG | Current Phase | Start Date | End Date | Progress | Status
Note: This is a free version of the template that allows you to manage up to 20 projects and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Instructions
Multi-Project Portfolio Planner - Instructions
FIELD | WHAT TO ENTER
Portfolio Name | Enter the portfolio or program name.
Portfolio Director | Name of the portfolio/PMO director.
PMO Lead | Name of the portfolio/PMO director.
Next Review | Next upcoming gate review or milestone.
Total Budget | Auto-calculated. Do not edit (grey cell).
Budget Utilized | Auto-calculated. Do not edit (grey cell).
Portfolio Health | Select from dropdown: Green — On track,Amber — At risk,Red — Critical issues
Reporting Period | Reporting period (e.g., Q3 2026).
Active Projects | Auto-calculated. Do not edit (grey cell).
🎯 Project Objective | 1-2 sentence project goal and measurable success criteria.
Created By | Name of the person who created this plan.
Created On | Date this plan was created (MM/DD/YYYY).
Last Updated | Date of last update (MM/DD/YYYY).
Completed | Auto-calculated. Do not edit (grey cell).
Avg Progress | Auto-calculated. Do not edit (grey cell).
Task Table Columns
ID | Unique task identifier (e.g., WF-01). Keep sequential.
Project Name | Project name for this row.
Project Manager | Project manager for this project.
Department | Department responsible.
Priority | Select from dropdown: Critical,High,Medium,Low
Budget | Budget allocated for this task/project.
RAG | Select from dropdown: Green,Amber,Red
Current Phase | Select from dropdown: Initiation,Planning,Requirements,Design,Build,Sprint 1,Sprint 2,Sprint 3,Pilot,Testing,Migration,Execution,UAT,Deployment,Hypercare,Closed
Start Date | Task start date (MM/DD/YYYY).
End Date | Task end date (MM/DD/YYYY).
Progress | Enter manually (0% to 100%). Update daily.
Status | Auto-calculated. Do not edit.
Gantt Chart | Auto-generated from Start/End dates. Do not edit. Bars update automatically.
Grey / Locked Cells
Light grey cells | Contain formulas - auto-calculated from your entries.
Formula bar blank | By design - formulas are hidden for protection.
Cannot edit | These cells are locked. Only white cells are editable.
Tips
Phase rows | Bold colored rows are section headers. Enter tasks below them.
Dropdowns | Click cells with small arrows to see available options.
Dates | Use MM/DD/YYYY format for all date fields.
Progress | Enter manually (0% to 100%). Update daily as work progresses.
Status | Auto-calculated from Progress. 100%=Completed, 1-99%=In progress, 0%=Not started.
Save often | File > Save As to create backup versions.
Need More Features?
More tasks | FREE version supports 25 tasks. Premium = unlimited tasks with auto-expanding rows.
Longer Gantt | FREE = 5-week Gantt. Premium = 9-week dynamic view with zoom in/out.
Unlimited Projects | Premium supports unlimited project sheets with one-click duplication.
Fully Unlocked | All cells editable. No locked sheets, no hidden formulas, no restrictions.
Fully Customizable | Easily customize colors, layout, and fields to suit any project type or industry.
Get Premium Template | Visit analysistabs.org/product/simple-multiple-project-tracking-template-excel/
Excel PM Templates by PNRao ¦ Excelx.com ¦ Powered by Analysistabs®

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms

## Analysistabs (hidden)
1
DO NOT DELETE OR MODIFY THIS SHEET
WARNING — SYSTEM SHEET
This sheet is required for the template to function correctly.
It contains essential configuration used by formulas, conditional formatting,
Gantt chart rendering, progress bars, and KPI calculations.
| If this sheet is deleted or modified: | 1
| • Gantt chart bars will stop rendering | 1
| • Progress bars will show errors | 1
• KPI cards will display #REF! errors
• Conditional formatting will break
• Auto-calculated fields will stop working
This sheet will be hidden when the template is exported.
Users will not see this sheet in the downloaded file.
Analysistabs® ¦ Excelx.com ¦ Template Configuration Sheet