## Project Charter
| PROJECT CHARTER |  | TOTAL BUDGET | SPENT | MILESTONES | APPROVALS
| One-page project authorization document · Scope · Objectives · Stakeholders · Approvals |  | $340,000 | 55.15% | 1 / 6 | 2 / 4
1 | PROJECT OVERVIEW
P1 | Project Name | Project Beacon: Customer Self-Service Portal |  |  | Project ID | PRJ-2026-0042
P2 | Project Manager | Catherine Reyes | Sponsor | VP of Product — James Liu | Department | Digital Products
P3 | Start Date | May 4, 2026 | End Date | August 14, 2026 | Priority | High
P4 | Budget | 340000 | Duration | 15 weeks | Status | Approved
2 | PROJECT PURPOSE & BUSINESS JUSTIFICATION
❗ | Business Problem | Currently 68% of customer inquiries require agent intervention. Average resolution time is 4.2 hours. Support costs have increased 35% YoY while CSAT dropped to 72%.
💡 | Proposed Solution | Build a self-service portal enabling customers to track orders, submit/manage support tickets, access knowledge base, and update account information without agent assistance.
🎯 | Expected Benefits | Reduce agent-handled inquiries by 40%, decrease resolution time to <1 hour, improve CSAT to 85%, and save $180K annually in support costs. Projected ROI: 18 months.
3 | OBJECTIVES & SUCCESS CRITERIA
# | Objective |  | Success Metric | Target | Measurement Method | Owner
O1 | Reduce agent-handled inquiries |  | % of inquiries self-served | 40% reduction | Monthly analytics report | Support Ops
O2 | Improve customer satisfaction |  | CSAT survey score | 85% or higher | Post-interaction survey | CX Team
O3 | Decrease average resolution time |  | Avg time to resolution | < 1 hour | Ticketing system data | Support Ops
O4 | Reduce annual support costs |  | Annual cost savings | $180K savings | Finance quarterly review | Finance
O5 | Achieve user adoption |  | Monthly active users | 5,000 MAU by Q4 | Portal analytics | Product
4 | PROJECT SCOPE
✓ | In Scope | Order tracking dashboard, Support ticket submission & management, Knowledge base with search, Account profile management, SSO integration with existing auth, Mobile-responsive design, Analytics & reporting dashboard
✕ | Out of Scope | Live chat / chatbot integration, Payment processing or billing changes, Third-party marketplace integrations, Native mobile app (web-responsive only), Legacy system decommission (separate project)
5 | KEY MILESTONES & TIMELINE
# | Milestone | Deliverable |  | Target Date | Owner | Status
M1 | Requirements sign-off | Approved BRD document |  | May 16, 2026 | Catherine Reyes | Completed
M2 | UX design approval | Signed-off wireframes & mockups |  | May 30, 2026 | James Liu (Sponsor) | In Progress
M3 | Development complete | All features coded & unit tested |  | June 26, 2026 | Dev Team | Not Started
M4 | UAT sign-off | UAT report with zero P1 defects |  | July 10, 2026 | Business Users | Not Started
M5 | Go-live | Portal live in production |  | July 24, 2026 | Catherine Reyes | Not Started
M6 | Post-launch review | 30-day performance report |  | August 14, 2026 | Catherine Reyes | Not Started
6 | KEY STAKEHOLDERS
# | Name | Title / Role | Department | Interest Level | Influence | Communication
S1 | James Liu | VP of Product (Sponsor) | Product | High | High | Weekly steering committee
S2 | Catherine Reyes | Project Manager | Digital Products | High | High | Daily standups + weekly report
S3 | Sarah Chen | Head of Support | Customer Support | High | Medium | Bi-weekly review meetings
S4 | David Park | CTO | Engineering | Medium | High | Monthly exec update
S5 | Karen Walsh | Finance Director | Finance | Medium | Medium | Monthly budget review
S6 | End Users | Beta testers (50 users) | Cross-department | High | Low | UAT sessions + survey
7 | RISKS, ASSUMPTIONS & CONSTRAINTS
⚠ | Key Risks | 1) Integration complexity with legacy ticketing system may delay development. 2) User adoption may be lower than projected if UX is not intuitive. 3) Budget overrun risk if scope creep occurs during UAT phase.
ⓘ | Assumptions | 1) Existing SSO infrastructure can support portal auth. 2) API documentation for ticketing system is accurate and current. 3) Business stakeholders available for requirements and UAT. 4) No major org changes during project.
🔒 | Constraints | 1) Fixed budget of $340,000 — no additional funding available. 2) Must use existing tech stack (React + Node.js). 3) Go-live must happen before August 1 to align with Q3 support restructuring. 4) Maximum 4 FTEs allocated.
8 | BUDGET SUMMARY
# | Category | Description | Amount | % of Total | Spent to Date | Remaining
B1 | Development | Frontend + backend + integrations | 180000 | 53% | 108000 | 72000
B2 | Design & UX | Wireframes, mockups, user research | 45000 | 13% | 42000 | 3000
B3 | Infrastructure | Cloud hosting, CDN, monitoring | 30000 | 9% | 18000 | 12000
B4 | Testing & QA | SIT, UAT, performance, security | 25000 | 7% | 8000 | 17000
B5 | Training | User guides, video tutorials, sessions | 15000 | 4% | 5000 | 10000
B6 | Project Management | PM tools, reporting, travel | 11000 | 3% | 6500 | 4500
B7 | Contingency | 10% reserve for unknowns | 34000 | 10% | 0 | 34000
Σ | TOTAL |  | $340,000 | 100% | 187500 | 152500
9 | APPROVAL & SIGN-OFF
# | Role | Name | Signature | Date | Status | Remarks
A1 | Project Sponsor | James Liu |  |  | Approved
A2 | Project Manager | Catherine Reyes |  |  | Approved
A3 | Finance Director | Karen Walsh |  |  | Rejected
A4 | CTO | David Park |  |  | Pending
Note: This is a free version of the Project Charter template. Visit excelx.com for premium templates. |  |  |  |  | EXCELX.COM · Premium Templates

## Instructions
| INSTRUCTIONS | Anlayistabs® Free Project Charter Templates | VERSION
| How to use this workbook · Sheet guide · Field definitions · Tips |  | v1.0
1 | WORKBOOK OVERVIEW
S1 | Project Charter | Main one-page charter. Fill in overview, objectives, scope, milestones, stakeholders, risks, budget, and approvals.
S2 | Instructions | This sheet — how to use the template and what each section means.
S3 | Free vs Premium | Comparison of the free template vs. the paid version's added features.
S4 | License | Terms of use for the template. Read before sharing or modifying.
2 | HOW TO FILL OUT THE CHARTER
# | Section | What to do
1 | Project Overview | Enter project name, manager, sponsor, dates, department, priority, status, project ID, and total budget in the top block.
2 | Purpose & Justification | Describe business problem (❗), proposed solution (💡), and expected benefits (🎯).
3 | Objectives | List up to 5 objectives (O1–O5) with success metric, target, measurement method, and owner.
4 | Scope | Define what is in scope (✓) and out of scope (✕) — out-of-scope is just as important to prevent scope creep.
5 | Milestones | List up to 6 milestones (M1–M6) with deliverable, owner, target date, and status. Header tracker counts 'Completed' automatically.
6 | Stakeholders | List up to 6 stakeholders (S1–S6) with role, department, interest, influence, and communication cadence.
7 | Risks / Assumptions / Constraints | Capture risks (⚠), assumptions (ⓘ), and constraints (🔒) — one cell each, numbered list inside.
8 | Budget | Enter Amount per category (B1–B7). Spent to Date is manual; % of Total and Remaining are formulas.
9 | Approvals | Capture approver name, signature, date, status, and remarks for each role (A1–A4). Header tracker counts 'Approved' automatically.
3 | LEGEND
❗ | Business Problem | What's wrong today — the pain that justifies doing the project.
💡 | Proposed Solution | How the project will solve the problem.
🎯 | Expected Benefits | Quantified outcomes and ROI.
✓ / ✕ | In Scope / Out of Scope | Boundaries of the project deliverables.
⚠ ⓘ 🔒 | Risks / Assumptions / Constraints | Things that could derail the project, things you're betting on, hard limits you must operate within.
Σ | Total / Summary Row | Auto-calculated total — do not overwrite.
4 | TIPS
• | Keep it to one page | Link out to detailed plans, BRDs, and risk registers rather than expanding the charter.
• | Update weekly | Refresh milestone Status and Spent-to-Date so the header KPIs (Spent %, Milestones, Approvals) stay accurate.
• | Don't overwrite formula cells | Header KPI tiles and budget totals are formulas. Edit the underlying tables; the headers update themselves.
• | Single source of truth | Use the Status field in Project Overview (Draft / In Review / Approved / Active / Closed) as the canonical state of the charter.

## Free vs Premium
Explore Anlayistabs® Premiun Project Management Templates
FREE vs PREMIUM PROJECT PLANNER
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)
Premium Project Charter Templates Pack
– Excel, PowerPoint & Word
Automated Calculations | Easy Tracking | Fully Customizable + 3 Project Dashboard Templates (Bonus)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms