## 9 Budget Tracking
| Project Plan with Budget Tracking | [8 empty] | TOTAL BUDGET | [6 empty] | SPENT | [6 empty] | REMAINING | [6 empty] | VARIANCE | [6 empty] | 🎢 Overall Progress |  |  | 33.4% |  |  | 0.334
| Budget-first Roadmap: 5-week cost-controlled delivery | [8 empty] | 142000 | [6 empty] | 58700 | [6 empty] | 83300 | [6 empty] | 83300
| Project Keystone: Office Automation | [42 empty] | 0.666
Project Details | Project Name | Project Keystone: Office Automation |  |  | Start Date | 2026-05-04 |  | Budget Status | On Track | 🎯 Project Objective | [6 empty] | Deploy office automation platform across 4 departments (HR, Finance, Operations, Sales) with automated workflows, document management, and reporting dashboards. Deliver within $142K budget including 10% contingency.
| Project Manager | Daniel Ortega |  |  | End Date | 2026-06-05 |  | Spent to Date | 41.34% | [29 empty] | Completed | 6
| Finance Lead | Karen Walsh | Created On | 2026-04-20 | Total Budget | 142000 |  | Forecast at Completion | 58700 | [29 empty] | In progress | 7
| Created By | Daniel Ortega | Last Updated | 2026-04-20 | Contingency | 14200 | 10% | Cost Variance | 83300 | [29 empty] | Not started | 9
Task Table | [9 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[10 empty] | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jun | Jun
ID | Task Name | Assigned To | Start Date | End Date | Planned Cost | Actual Cost | Variance | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
PHASE 1: REQUIREMENTS & PLANNING
BT-01 | Business requirements workshops (4 depts) | Daniel Ortega | 2026-05-04 | 2026-05-07 | 5000 | 3000 | 2000 | 100% | Completed
BT-02 | Vendor evaluation & RFP scoring | Karen Walsh | 2026-05-05 | 2026-05-09 | 3000 | 3000 | 0 | 100% | Completed
BT-03 | Solution architecture & tech design | Raj Patel | 2026-05-06 | 2026-05-12 | 8000 | 7500 | 500 | 100% | Completed
BT-04 | Contract negotiation & procurement | Karen Walsh | 2026-05-08 | 2026-05-12 | 2000 | 2200 | -200 | 100% | Completed
BT-05 | Project plan & budget baseline sign-off | Daniel Ortega | 2026-05-12 | 2026-05-12 | 1000 | 1000 | 0 | 100% | Completed
PHASE 2: PLATFORM SETUP & CONFIG
BT-06 | Cloud environment provisioning | Raj Patel | 2026-05-11 | 2026-05-14 | 12000 | 11500 | 500 | 100% | Completed
BT-07 | Core platform installation & licensing | Raj Patel | 2026-05-13 | 2026-05-16 | 25000 | 25000 | 0 | 80% | In progress
BT-08 | User directory sync (Active Directory) | Tina Gomez | 2026-05-14 | 2026-05-18 | 4000 | 2000 | 2000 | 60% | In progress
BT-09 | Department-specific workflow config | Tina Gomez | 2026-05-15 | 2026-05-20 | 8000 | 3000 | 5000 | 40% | In progress
BT-10 | Document template library setup | Daniel Ortega | 2026-05-16 | 2026-05-20 | 3000 | 500 | 2500 | 20%
PHASE 3: INTEGRATION & DATA
BT-11 | ERP integration (SAP connector) | Raj Patel | 2026-05-18 | 2026-05-23 | 15000 | 0 | 15000 | 15% | In progress
BT-12 | CRM integration (Salesforce sync) | Raj Patel | 2026-05-19 | 2026-05-26 | 12000 | 0 | 12000 | 10% | In progress
BT-13 | Historical data migration & cleanup | Tina Gomez | 2026-05-20 | 2026-05-27 | 6000 | 0 | 6000 | 5% | In progress
BT-14 | Reporting dashboard development | Tina Gomez | 2026-05-21 | 2026-05-28 | 8000 | 0 | 8000 | 5% | In progress
BT-15 | API gateway & security hardening | Raj Patel | 2026-05-22 | 2026-05-28 | 5000 | 0 | 5000 | 0% | Not started
PHASE 4: TESTING & TRAINING
BT-16 | System integration testing (SIT) | Tina Gomez | 2026-05-26 | 2026-05-29 | 4000 | 0 | 4000 | 0% | Not started
BT-17 | User acceptance testing — HR dept | Daniel Ortega | 2026-05-27 | 2026-05-29 | 2000 | 0 | 2000 | 0% | Not started
BT-18 | User acceptance testing — Finance dept | Karen Walsh | 2026-05-28 | 2026-06-01 | 2000 | 0 | 2000 | 0% | Not started
BT-19 | Defect resolution & retesting | Raj Patel | 2026-05-29 | 2026-06-02 | 3000 | 0 | 3000 | 0% | Not started
BT-20 | End-user training (4 dept sessions) | Daniel Ortega | 2026-05-29 | 2026-06-03 | 6000 | 0 | 6000 | 0% | Not started
PHASE 5: GO-LIVE & CLOSURE
BT-21 | Production deployment & cutover | Raj Patel | 2026-06-01 | 2026-06-02 | 3000 | 0 | 3000 | 0% | Not started
BT-22 | Post-deployment verification | Tina Gomez | 2026-06-02 | 2026-06-03 | 1000 | 0 | 1000 | 0%
BT-23 | Hypercare support (5 days) | All Team | 2026-06-01 | 2026-06-05 | 2000 | 0 | 2000 | 0%
BT-24 | Final budget reconciliation & report | Karen Walsh | 2026-06-04 | 2026-06-05 | 1000 | 0 | 1000 | 0% | Not started
BT-25 | Project closure & lessons learned | Daniel Ortega | 2026-06-05 | 2026-06-05 | 1000 | 0 | 1000 | 0% | Not started
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Blank Template
| Project Plan with Budget Tracking | [8 empty] | TOTAL BUDGET | [6 empty] | SPENT | [6 empty] | REMAINING | [6 empty] | VARIANCE | [6 empty] | 🎢 Overall Progress |  |  | 0% |  |  | 0
| Budget-first Roadmap: 5-week cost-controlled delivery | [8 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
1
Project Details | Project Name |  |  |  | Start Date |  |  | Budget Status | On Track | 🎯 Project Objective
| Project Manager |  |  |  | End Date |  |  | Spent to Date | [30 empty] | Completed | 0
| Finance Lead |  | Created On |  | Total Budget | 0 |  | Forecast at Completion | 0 | [29 empty] | In progress | 0
| Created By |  | Last Updated |  | Contingency | 0 |  | Cost Variance | 0 | [29 empty] | Not started | 0
Task Table | [9 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[10 empty] | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jun | Jun
ID | Task Name | Assigned To | Start Date | End Date | Planned Cost | Actual Cost | Variance | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Instructions
Project Plan with Budget Tracking - Instructions
FIELD | WHAT TO ENTER
Project Name | Enter your project name (e.g., Website Redesign, ERP Migration).
Project Manager | Name of the person managing this project.
Finance Lead | Finance team lead name.
Start Date | Auto-calculated. Do not edit (grey cell).
End Date | Auto-calculated. Do not edit (grey cell).
Budget Status | Auto-calculated. Do not edit (grey cell).
Total Budget | Auto-calculated. Do not edit (grey cell).
Contingency | Auto-calculated. Do not edit (grey cell).
Spent to Date | Auto-calculated. Do not edit (grey cell).
Forecast at Completion | Auto-calculated. Do not edit (grey cell).
Cost Variance | Auto-calculated. Do not edit (grey cell).
🎯 Project Objective | 1-2 sentence project goal and measurable success criteria.
Created By | Name of the person who created this plan.
Created On | Date this plan was created (MM/DD/YYYY).
Last Updated | Date of last update (MM/DD/YYYY).
Task Table Columns
ID | Unique task identifier (e.g., WF-01). Keep sequential.
Task Name | Clear, action-oriented task description.
Assigned To | Team member responsible for this task.
Start Date | Task start date (MM/DD/YYYY).
End Date | Task end date (MM/DD/YYYY).
Planned Cost | Budgeted cost for this task.
Actual Cost | Actual amount spent on this task.
Variance | Auto-calculated. Do not edit.
Progress | Enter manually (0% to 100%). Update daily.
Status | Auto-calculated. Do not edit.
Gantt Chart | Auto-generated from Start/End dates. Do not edit. Bars update automatically.
Grey / Locked Cells
Light grey cells | Contain formulas - auto-calculated from your entries.
Formula bar blank | By design - formulas are hidden for protection.
Cannot edit | These cells are locked. Only white cells are editable.
Tips
Phase rows | Bold colored rows are section headers. Enter tasks below them.
Dropdowns | Click cells with small arrows to see available options.
Dates | Use MM/DD/YYYY format for all date fields.
Progress | Enter manually (0% to 100%). Update daily as work progresses.
Status | Auto-calculated from Progress. 100%=Completed, 1-99%=In progress, 0%=Not started.
Save often | File > Save As to create backup versions.
Need More Features?
More tasks | FREE version supports 25 tasks. Premium = unlimited tasks with auto-expanding rows.
Longer Gantt | FREE = 5-week Gantt. Premium = 9-week dynamic view with zoom in/out.
Unlimited Projects | Premium supports unlimited project sheets with one-click duplication.
Fully Unlocked | All cells editable. No locked sheets, no hidden formulas, no restrictions.
Fully Customizable | Easily customize colors, layout, and fields to suit any project type or industry.
Get Premium Template | Visit analysistabs.org/product/simple-multiple-project-tracking-template-excel/
Excel PM Templates by PNRao ¦ Excelx.com ¦ Powered by Analysistabs®

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms

## Analysistabs (hidden)
1
DO NOT DELETE OR MODIFY THIS SHEET
WARNING — SYSTEM SHEET
This sheet is required for the template to function correctly.
It contains essential configuration used by formulas, conditional formatting,
Gantt chart rendering, progress bars, and KPI calculations.
| If this sheet is deleted or modified: | 1
| • Gantt chart bars will stop rendering | 1
| • Progress bars will show errors | 1
• KPI cards will display #REF! errors
• Conditional formatting will break
• Auto-calculated fields will stop working
This sheet will be hidden when the template is exported.
Users will not see this sheet in the downloaded file.
Analysistabs® ¦ Excelx.com ¦ Template Configuration Sheet