## #22 Resource Allocation
| Project Plan with Resource Allocation |  |  |  | TEAM MEMBERS |  |  |  | OVERALLOCATED |  | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | IN PROGRESS | [6 empty] | NOT STARTED | [6 empty] | 🎢 Overall Progress |  |  | 39.4% |  |  | 0.394
| Resource-optimized Roadmap: WBS-structured with team capacity |  |  |  | 5 |  |  |  | 4 |  | 25 | [6 empty] | 6 | [6 empty] | 9 | [6 empty] | 10
| Project Pinnacle: E-Commerce Platform Rebuild | [43 empty] | 0.606
Project Details | Project Name | Project Pinnacle: E-Commerce Platform Rebuild |  |  | Team Capacity | 5 FTEs × 40 hrs/wk = 200 hrs/wk |  |  | Start Date | 2026-05-04 | 🎯 Project Objective | [6 empty] | Rebuild e-commerce platform with new product catalog, shopping cart, payment gateway, and order management. Migrate 15,000 SKUs, integrate with 3 shipping providers, and launch with zero-downtime cutover.
| Project Manager | David Nakamura |  |  | Budget | 310000 |  |  | End Date | 2026-06-03 | [29 empty] | Completed | 6
| Department | Operations & Technology | Created On | 2026-05-04 | Critical Path | NX-03 → NX-08 → NX-14 → NX-20 |  |  | Total Hours | 95 | [29 empty] | In progress | 9
| Created By | David Nakamura | Last Updated | 2026-05-04 | Resource Risk | Frontend dev overallocated Wk 3 |  |  | Utilization Avg | 32.16% | [29 empty] | Not started | 10
Task Table | [10 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[11 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
WBS | Phase/Task Name | Assigned To | Start Date | Predecessor | Duration | Planned Hrs | Progress | Status | Planned Start | Planned End | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
PHASE 1: ANALYSIS & PLANNING
NX-01 | Current platform audit & gap analysis | David Nakamura | 2026-05-04 |  | 4 | 3 | 100% | Completed | 2026-05-04 | 2026-05-07
NX-02 | Gather requirements from stakeholders | Sophie Larsen | 2026-05-05 | NX-01 | 5 | 2 | 100% | Completed | 2026-05-04 | 2026-05-08
NX-03 | Vendor & payment gateway evaluation | David Nakamura | 2026-05-06 | NX-01 | 4 | 3 | 100% | Completed | 2026-05-04 | 2026-05-07
NX-04 | Technical architecture & API design | Ravi Deshmukh | 2026-05-08 | NX-02 | 7 | 2 | 100% | Completed | 2026-05-05 | 2026-05-11
NX-05 | Project schedule & resource plan | David Nakamura | 2026-05-09 | NX-03 | 4 | 1 | 100% | Completed | 2026-05-06 | 2026-05-09
PHASE 2: CORE DEVELOPMENT
NX-06 | Product catalog & search engine | Ravi Deshmukh | 2026-05-12 | NX-04 | 7 | 3 | 100% | Completed | 2026-05-08 | 2026-05-14
NX-07 | Shopping cart & checkout flow | Ravi Deshmukh | 2026-05-13 | NX-04 | 8 | 3 | 90% | In progress | 2026-05-08 | 2026-05-15
NX-08 | Payment gateway integration (Stripe) | Ravi Deshmukh | 2026-05-18 | NX-06 | 6 | 3 | 70% | In progress | 2026-05-12 | 2026-05-17
NX-09 | User account & order history portal | Sophie Larsen | 2026-05-15 | NX-03 | 8 | 3 | 60% | In progress | 2026-05-06 | 2026-05-13
NX-10 | Shipping provider API integration (3) | Chloe Adebayo | 2026-05-19 | NX-07 | 5 | 6 | 50% | In progress | 2026-05-13 | 2026-05-17
PHASE 3: FRONTEND & UX
NX-11 | Product listing & detail pages UI | Chloe Adebayo | 2026-05-20 | NX-08 | 8 | 5 | 40% | In progress | 2026-05-18 | 2026-05-25
NX-12 | Cart, checkout & payment UI | Sophie Larsen | 2026-05-21 | NX-07 | 7 | 6 | 30% | In progress | 2026-05-13 | 2026-05-19
NX-13 | Order tracking & account dashboard | Sophie Larsen | 2026-05-22 | NX-09 | 7 | 7 | 20% | In progress | 2026-05-15 | 2026-05-21
NX-14 | Mobile-responsive design & PWA | Ravi Deshmukh | 2026-05-22 | NX-07 | 6 | 7 | 15% | In progress | 2026-05-13 | 2026-05-18
NX-15 | Admin panel (inventory & orders) | Chloe Adebayo | 2026-05-25 | NX-12 | 5 | 7 | 10% | In progress | 2026-05-21 | 2026-05-25
PHASE 4: TESTING & VALIDATION
NX-16 | Unit & integration testing | Sophie Larsen | 2026-05-26 | NX-11 | 4 | 4 | 0% | Not started | 2026-05-20 | 2026-05-23
NX-17 | Payment flow UAT (3 gateways) | Sophie Larsen | 2026-05-27 | NX-13 | 6 | 3 | 0% | Not started | 2026-05-22 | 2026-05-27
NX-18 | Load testing (10K concurrent users) | Sophie Larsen | 2026-05-28 | NX-14 | 5 | 4 | 0% | Not started | 2026-05-22 | 2026-05-26
NX-19 | Performance & SEO optimization | Ravi Deshmukh | 2026-05-29 | NX-16 | 5 | 4 | 0% | Not started | 2026-05-26 | 2026-05-30
NX-20 | Security audit & PCI compliance | Sophie Larsen | 2026-06-01 | NX-16 | 3 | 3 | 0% | Not started | 2026-05-26 | 2026-05-28
PHASE 5: DEPLOYMENT & HANDOVER
NX-21 | Production deployment & data migration | Ravi Deshmukh | 2026-06-03 | NX-20 | 2 | 6 | 0% | Not started | 2026-06-01 | 2026-06-02
NX-22 | Team training (2 sessions) | Sophie Larsen | 2026-06-02 | NX-18 | 3 | 2 | 0% | Not started | 2026-05-28 | 2026-05-30
NX-23 | Vendor onboarding (top 10 sellers) | David Nakamura | 2026-06-03 | NX-17 | 3 | 2 | 0% | Not started | 2026-05-27 | 2026-05-29
NX-24 | Hypercare & monitoring (5 days) | David Nakamura | 2026-06-01 | NX-21 | 1 | 5 | 0% | Not started | 2026-06-03 | 2026-06-03
NX-25 | Project handover & documentation | David Nakamura | 2026-06-05 | NX-24 | 1 | 1 | 0% | Not started | 2026-06-01 | 2026-06-01
Team Members | [10 empty] | 2026-05-04: WEEK 19; 2026-05-11: WEEK 20; 2026-05-18: WEEK 21; 2026-05-25: WEEK 22; 2026-06-01: WEEK 23
[11 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Name | Role | Tasks Allocated | Planned Hrs | Avg Progress | Peak Daily Load | Overallocated | Completed | In Progress | Not Started | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
EMP-001 | David Nakamura | Project Manager | 6 | 15 | 50% | 3 | ⚠️ Yes | 3 | 0 | 3 | 2 | 2 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
EMP-002 | Sophie Larsen | QA Lead | 9 | 34 | 23.33% | 3 | ⚠️ Yes | 1 | 3 | 5 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EMP-003 | Ravi Deshmukh | Full-Stack Developer | 7 | 28 | 53.57% | 4 | ⚠️ Yes | 2 | 3 | 2 | 0 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
EMP-004 | Sophie Larsen | Frontend Developer | 9 | 34 | 23.33% | 3 | ⚠️ Yes | 1 | 3 | 5 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EMP-005 | Chloe Adebayo | UX / Frontend | 3 | 18 | 33.33% | 2 | OK | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: This is a free version of the template that allows you to manage up to 35 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Blank Template
| Project Plan with Resource Allocation |  |  |  | TEAM MEMBERS |  |  |  | OVERALLOCATED |  | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | IN PROGRESS | [6 empty] | NOT STARTED | [6 empty] | 🎢 Overall Progress |  |  | 0% |  |  | 0
| Resource-optimized Roadmap: WBS-structured with team capacity |  |  |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
1
Project Details | Project Name |  |  |  | Team Capacity |  |  |  | Start Date |  | 🎯 Project Objective
| Project Manager |  |  |  | Budget |  |  |  | End Date | [30 empty] | Completed | 0
| Department |  | Created On |  | Critical Path |  |  |  | Total Hours | 0 | [29 empty] | In progress | 0
| Created By |  | Last Updated |  | Resource Risk |  |  |  | Utilization Avg | 0% | [29 empty] | Not started | 0
Task Table | [10 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[11 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
WBS | Phase/Task Name | Assigned To | Start Date | Predecessor | Duration | Planned Hrs | Progress | Status | Planned Start | Planned End | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
Team Members | [10 empty] | 2026-05-04: #NUM!; 2026-05-11: WEEK 20; 2026-05-18: WEEK 21; 2026-05-25: WEEK 22; 2026-06-01: WEEK 23
[11 empty] | #VALUE! | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Name | Role | Tasks Allocated | Planned Hrs | Avg Progress | Peak Daily Load | Overallocated | Completed | In Progress | Not Started | -5 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
Note: This is a free version of the template that allows you to manage up to 35 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Instructions
Project Plan with Resource Allocation - Instructions
STEP 1 | Fill Team Members Table First (Bottom of Sheet)
IMPORTANT | You MUST fill the Team Members table BEFORE entering tasks. Scroll down below the Task Table to find it.
ID | Unique member ID (e.g., EMP-001, EMP-002). Keep sequential.
Name | REQUIRED. Full name of the team member. This name appears in the Assigned To dropdown in the Task Table.
Role | Team member's role (e.g., Project Manager, Developer, QA Lead).
Tasks Allocated | Auto-calculated. Shows how many tasks are assigned to this person. Do not edit.
Planned Hrs | Auto-calculated. Total planned hours across all assigned tasks. Do not edit.
Avg Progress | Auto-calculated. Average progress of all assigned tasks. Do not edit.
Peak Daily Load | Auto-calculated. Maximum tasks running on any single day. Do not edit.
Overallocated | Auto-calculated. Shows Yes/No if member exceeds daily capacity. Do not edit.
Completed | Auto-calculated. Count of completed tasks for this member. Do not edit.
In Progress | Auto-calculated. Count of in-progress tasks for this member. Do not edit.
Not Started | Auto-calculated. Count of not-started tasks for this member. Do not edit.
FIELD | WHAT TO ENTER
Project Name | Enter your project name (e.g., Website Redesign, ERP Migration).
Project Manager | Name of the person managing this project.
Department | Your department or client name.
Start Date | Auto-calculated. Do not edit (grey cell).
End Date | Auto-calculated. Do not edit (grey cell).
Budget | Total project budget (e.g., $150,000).
Team Capacity | Team capacity (e.g., 5 FTEs x 40 hrs/wk = 200 hrs/wk).
Critical Path | Critical path task chain (e.g., T3 > T8 > T14 > T20).
Resource Risk | Resource risk description (e.g., Dev overallocated Wk 3).
Utilization Avg | Auto-calculated. Do not edit (grey cell).
Total Hours | Auto-calculated. Do not edit (grey cell).
🎯 Project Objective | 1-2 sentence project goal and measurable success criteria.
Created By | Name of the person who created this plan.
Created On | Date this plan was created (MM/DD/YYYY).
Last Updated | Date of last update (MM/DD/YYYY).
Completed | Auto-calculated. Do not edit (grey cell).
6 | Enter the 6 value.
In progress | Auto-calculated. Do not edit (grey cell).
9 | Enter the 9 value.
Not started | Auto-calculated. Do not edit (grey cell).
10 | Enter the 10 value.
Task Table Columns
WBS | Work Breakdown Structure number (e.g., 1.1, 2.3). Hierarchical.
Phase/Task Name | Clear, action-oriented task description.
Assigned To | Select from dropdown: =$C$48:$C$57
Start Date | Task start date (MM/DD/YYYY).
Predecessor | ID of the task that must finish before this one starts.
Duration | Number of working days for this task.
Planned Hrs | Estimated hours for this task.
Progress | Enter manually (0% to 100%). Update daily.
Status | Auto-calculated. Do not edit.
Planned Start | Auto-calculated. Do not edit.
Planned End | Auto-calculated. Do not edit.
Gantt Chart | Auto-generated from Start/End dates. Do not edit. Bars update automatically.
Grey / Locked Cells
Light grey cells | Contain formulas - auto-calculated from your entries.
Formula bar blank | By design - formulas are hidden for protection.
Cannot edit | These cells are locked. Only white cells are editable.
Tips
Phase rows | Bold colored rows are section headers. Enter tasks below them.
Dropdowns | Click cells with small arrows to see available options.
Dates | Use MM/DD/YYYY format for all date fields.
Progress | Enter manually (0% to 100%). Update daily as work progresses.
Status | Auto-calculated from Progress. 100%=Completed, 1-99%=In progress, 0%=Not started.
Save often | File > Save As to create backup versions.
Need More Features?
More tasks | FREE version supports 25 tasks. Premium = unlimited tasks with auto-expanding rows.
Longer Gantt | FREE = 5-week Gantt. Premium = 9-week dynamic view with zoom in/out.
Unlimited Projects | Premium supports unlimited project sheets with one-click duplication.
Fully Unlocked | All cells editable. No locked sheets, no hidden formulas, no restrictions.
Fully Customizable | Easily customize colors, layout, and fields to suit any project type or industry.
Get Premium Template | Visit analysistabs.org/product/simple-multiple-project-tracking-template-excel/
Excel PM Templates by PNRao ¦ Excelx.com ¦ Powered by Analysistabs®

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms

## Analysistabs (hidden)
1
DO NOT DELETE OR MODIFY THIS SHEET
WARNING — SYSTEM SHEET
This sheet is required for the template to function correctly.
It contains essential configuration used by formulas, conditional formatting,
Gantt chart rendering, progress bars, and KPI calculations.
| If this sheet is deleted or modified: | 1
| • Gantt chart bars will stop rendering | 1
| • Progress bars will show errors | 1
• KPI cards will display #REF! errors
• Conditional formatting will break
• Auto-calculated fields will stop working
This sheet will be hidden when the template is exported.
Users will not see this sheet in the downloaded file.
Analysistabs® ¦ Excelx.com ¦ Template Configuration Sheet