## #5 Timeline
| Project Plan with Timeline & Milestones | [6 empty] | TOTAL TASKS |  | MILESTONES | [5 empty] | COMPLETED | [6 empty] | ON TRACK | [6 empty] | AT RISK | [6 empty] | 🎢 Overall Progress |  |  | 37.8% |  |  | 0.378
| Milestone-driven Roadmap: 5-week delivery schedule | [6 empty] | 25 |  | 6 | [5 empty] | 1 | [6 empty] | 5 | [6 empty] | 0
| Project Summit: Brand Refresh & Relaunch | [41 empty] | 0.622
Project Details | Project Name | Project Summit: Brand Refresh & Relaunch |  |  | Start Date | 2026-05-04 | Sponsor | CMO — Patricia Nguyen | 🎯 Project Objective | [6 empty] | Execute complete brand refresh including new visual identity, messaging framework, and website relaunch. Deliver updated brand assets, style guide, and responsive website by June 5 launch date.
| Project Manager | Laura Bennett |  |  | End Date | 2026-06-05 | Budget | 165000 | [29 empty] | Completed | 6
| Department | Brand & Communications | Created On | 2026-04-20 | Total Milestones | 6 | Milestones Hit | 2 of 6 | [29 empty] | In progress | 7
| Created By | Laura Bennett | Last Updated | 2026-04-20 | Next Milestone | Design Review (May 16) | Days Left | 28 | [29 empty] | Not started | 10
Task Table | [8 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Task Name | Milestone? | Target Date | Assigned To | Start Date | End Date | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
| PHASE 1: DISCOVERY & STRATEGY | FALSE
TL-01 | Brand audit & competitive analysis | FALSE |  | Laura Bennett | 2026-05-04 | 2026-05-07 | 100% | Completed
TL-02 | Stakeholder interviews (8 sessions) | FALSE |  | Jake Morrison | 2026-05-04 | 2026-05-08 | 100% | Completed
TL-03 | Customer perception survey analysis | FALSE |  | Priya Desai | 2026-05-05 | 2026-05-09 | 100% | Completed
TL-04 | Brand positioning & messaging framework | FALSE |  | Laura Bennett | 2026-05-07 | 2026-05-12 | 100% | Completed
TL-05 | Strategy presentation & approval | TRUE | 2026-05-12 | Laura Bennett | 2026-05-12 | 2026-05-12 | 100% | Completed
| PHASE 2: VISUAL IDENTITY DESIGN | FALSE
TL-06 | Logo concepts & exploration (5 options) | FALSE |  | Sasha Volkov | 2026-05-11 | 2026-05-15 | 100% | Completed
TL-07 | Color palette & typography selection | FALSE |  | Sasha Volkov | 2026-05-12 | 2026-05-15 | 90% | In progress
TL-08 | Icon set & illustration style | FALSE |  | Sasha Volkov | 2026-05-13 | 2026-05-16 | 70% | In progress
TL-09 | Brand style guide (v1 draft) | FALSE |  | Priya Desai | 2026-05-14 | 2026-05-19 | 50% | In progress
TL-10 | Design review & stakeholder feedback | TRUE | 2026-05-19 | Laura Bennett | 2026-05-19 | 2026-05-19 | 0% | Not started
| PHASE 3: WEBSITE REDESIGN & BUILD | FALSE
TL-11 | Sitemap & information architecture | FALSE |  | Jake Morrison | 2026-05-15 | 2026-05-19 | 60% | In progress
TL-12 | Wireframes — homepage & 5 key pages | FALSE |  | Sasha Volkov | 2026-05-18 | 2026-05-22 | 40% | In progress
TL-13 | UI design mockups (desktop + mobile) | FALSE |  | Sasha Volkov | 2026-05-20 | 2026-05-26 | 20% | In progress
TL-14 | Frontend development (HTML/CSS/JS) | FALSE |  | Dev Team | 2026-05-22 | 2026-05-29 | 10%
TL-15 | CMS integration & content migration | FALSE |  | Jake Morrison | 2026-05-25 | 2026-05-29 | 5% | In progress
TL-16 | Website dev complete — internal review | TRUE | 2026-05-29 | Laura Bennett | 2026-05-29 | 2026-05-29 | 0% | Not started
| PHASE 4: TESTING & CONTENT | FALSE
TL-17 | Cross-browser & responsive testing | FALSE |  | Dev Team | 2026-05-27 | 2026-05-29 | 0% | Not started
TL-18 | SEO audit & metadata optimization | FALSE |  | Priya Desai | 2026-05-28 | 2026-06-01 | 0% | Not started
TL-19 | Content proofing & legal review | FALSE |  | Jake Morrison | 2026-05-29 | 2026-06-01 | 0% | Not started
TL-20 | Accessibility (WCAG 2.1) compliance | FALSE |  | Dev Team | 2026-05-29 | 2026-06-02 | 0% | Not started
TL-21 | UAT sign-off from stakeholders | TRUE | 2026-06-02 | Laura Bennett | 2026-06-02 | 2026-06-02 | 0% | Not started
| PHASE 5: LAUNCH & ROLLOUT | FALSE
TL-22 | Finalize brand style guide (v2 final) | FALSE |  | Priya Desai | 2026-06-01 | 2026-06-03 | 0% | Not started
TL-23 | DNS switch & website go-live | TRUE | 2026-06-04 | Dev Team | 2026-06-04 | 2026-06-04 | 0% | Not started
TL-24 | Internal brand launch announcement | FALSE |  | Laura Bennett | 2026-06-04 | 2026-06-04 | 0%
TL-25 | Post-launch monitoring & brand handover | TRUE | 2026-06-05 | Laura Bennett | 2026-06-05 | 2026-06-05 | 0% | Not started
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Blank Template
| Project Plan with Timeline & Milestones | [6 empty] | TOTAL TASKS |  | MILESTONES | [5 empty] | COMPLETED | [6 empty] | ON TRACK | [6 empty] | AT RISK | [6 empty] | 🎢 Overall Progress |  |  | 0% |  |  | 0
| Milestone-driven Roadmap: 5-week delivery schedule | [6 empty] | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
1
Project Details | Project Name |  |  |  | Start Date |  | Sponsor |  | 🎯 Project Objective
| Project Manager |  |  |  | End Date |  | Budget | [30 empty] | Completed | 0
| Department |  | Created On |  | Total Milestones |  | Milestones Hit | [30 empty] | In progress | 0
| Created By |  | Last Updated |  | Next Milestone |  | Days Left | [30 empty] | Not started | 0
Task Table | [8 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Task Name | Milestone? | Target Date | Assigned To | Start Date | End Date | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Instructions
Project Plan with Timeline & Milestones - Instructions
FIELD | WHAT TO ENTER
Project Name | Enter your project name (e.g., Website Redesign, ERP Migration).
Project Manager | Name of the person managing this project.
Department | Your department or client name.
Start Date | Auto-calculated. Do not edit (grey cell).
End Date | Auto-calculated. Do not edit (grey cell).
Days Left | Auto-calculated. Do not edit (grey cell).
Next Milestone | Next upcoming gate review or milestone.
Budget | Total project budget (e.g., $150,000).
Sponsor | Executive sponsor name and title.
Total Milestones | Total number of milestones in the project.
Milestones Hit | Number of milestones completed (e.g., 2 of 6).
🎯 Project Objective | 1-2 sentence project goal and measurable success criteria.
Created By | Name of the person who created this plan.
Created On | Date this plan was created (MM/DD/YYYY).
Last Updated | Date of last update (MM/DD/YYYY).
Task Table Columns
ID | Unique task identifier (e.g., WF-01). Keep sequential.
Task Name | Clear, action-oriented task description.
Milestone? | Check if this task is a milestone (checkbox).
Target Date | Milestone target date (MM/DD/YYYY).
Assigned To | Team member responsible for this task.
Start Date | Task start date (MM/DD/YYYY).
End Date | Task end date (MM/DD/YYYY).
Progress | Enter manually (0% to 100%). Update daily.
Status | Auto-calculated. Do not edit.
Gantt Chart | Auto-generated from Start/End dates. Do not edit. Bars update automatically.
Grey / Locked Cells
Light grey cells | Contain formulas - auto-calculated from your entries.
Formula bar blank | By design - formulas are hidden for protection.
Cannot edit | These cells are locked. Only white cells are editable.
Tips
Phase rows | Bold colored rows are section headers. Enter tasks below them.
Dropdowns | Click cells with small arrows to see available options.
Dates | Use MM/DD/YYYY format for all date fields.
Progress | Enter manually (0% to 100%). Update daily as work progresses.
Status | Auto-calculated from Progress. 100%=Completed, 1-99%=In progress, 0%=Not started.
Save often | File > Save As to create backup versions.
Need More Features?
More tasks | FREE version supports 25 tasks. Premium = unlimited tasks with auto-expanding rows.
Longer Gantt | FREE = 5-week Gantt. Premium = 9-week dynamic view with zoom in/out.
Unlimited Projects | Premium supports unlimited project sheets with one-click duplication.
Fully Unlocked | All cells editable. No locked sheets, no hidden formulas, no restrictions.
Fully Customizable | Easily customize colors, layout, and fields to suit any project type or industry.
Get Premium Template | Visit analysistabs.org/product/simple-multiple-project-tracking-template-excel/
Excel PM Templates by PNRao ¦ Excelx.com ¦ Powered by Analysistabs®

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms

## Analysistabs (hidden)
1
DO NOT DELETE OR MODIFY THIS SHEET
WARNING — SYSTEM SHEET
This sheet is required for the template to function correctly.
It contains essential configuration used by formulas, conditional formatting,
Gantt chart rendering, progress bars, and KPI calculations.
| If this sheet is deleted or modified: | 1
| • Gantt chart bars will stop rendering | 1
| • Progress bars will show errors | 1
• KPI cards will display #REF! errors
• Conditional formatting will break
• Auto-calculated fields will stop working
This sheet will be hidden when the template is exported.
Users will not see this sheet in the downloaded file.
Analysistabs® ¦ Excelx.com ¦ Template Configuration Sheet