## Project Plan
| Project Plan 2026 | [5 empty] | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | IN PROGRESS | [6 empty] | NOT STARTED | [6 empty] | 🎢 Overall Progress |  |  | 40.6% |  |  | 0.406
| Task-based Roadmap: 8-week project lifecycle | [5 empty] | 25 | [6 empty] | 7 | [6 empty] | 9 | [6 empty] | 9
| Project Atlas: Enterprise CRM Migration | [39 empty] | 0.594
Project Details | Project Name | Project Atlas: Enterprise CRM Migration |  |  | Start Date | 2026-05-04 | 🎯 Project Objective | [6 empty] | Migrate 2,500 users from legacy CRM to Salesforce with zero data loss, completing training for all departments before Q3 go-live.
| Project Manager | Rachel Torres |  |  | End Date | 2026-06-07 | [29 empty] | Completed | 7
| Department / Client | IT Operations | Created On | 2026-05-04 | Duration | 35 | [29 empty] | In progress | 9
| Created By | Rachel Torres | Last Updated | 2026-06-26 | Days Left | 30 | [29 empty] | Not started | 9
Task Table | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Task Name | Assigned To | Start Date | End Date | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
WF-01 | Draft project charter & scope document | Rachel Torres | 2026-05-04 | 2026-05-06 | 100% | Completed
WF-02 | Identify key stakeholders & sponsors | Rachel Torres | 2026-05-04 | 2026-05-05 | 100% | Completed
WF-03 | Conduct feasibility assessment | James Liu | 2026-05-05 | 2026-05-08 | 100% | Completed
WF-04 | Secure budget approval & resources | Rachel Torres | 2026-05-07 | 2026-05-11 | 100% | Completed
WF-05 | Kick-off meeting with all stakeholders | Rachel Torres | 2026-05-11 | 2026-05-11 | 100% | Completed
WF-06 | Create detailed work breakdown structure | James Liu | 2026-05-12 | 2026-05-15 | 100% | Completed
WF-07 | Define milestones & deliverables | Rachel Torres | 2026-05-13 | 2026-05-15 | 100% | Completed
WF-08 | Develop resource allocation plan | Priya Sharma | 2026-05-14 | 2026-05-18 | 80% | In progress
WF-09 | Create risk register & mitigation plan | James Liu | 2026-05-15 | 2026-05-19 | 60% | In progress
WF-10 | Build communication & reporting plan | Rachel Torres | 2026-05-18 | 2026-05-20 | 50% | In progress
WF-11 | Finalize project schedule & baseline | Rachel Torres | 2026-05-19 | 2026-05-22 | 40% | In progress
WF-12 | Data audit & cleansing from legacy CRM | Marcus Johnson | 2026-05-20 | 2026-05-28 | 30% | In progress
WF-13 | Configure Salesforce environment | Priya Sharma | 2026-05-22 | 2026-06-01 | 20% | In progress
WF-14 | Build data migration scripts & mapping | Marcus Johnson | 2026-05-26 | 2026-06-03 | 15% | In progress
WF-15 | Develop custom reports & dashboards | Priya Sharma | 2026-05-28 | 2026-06-05 | 10% | In progress
WF-16 | Integration with email & calendar | Marcus Johnson | 2026-05-22 | 2026-05-26 | 0% | Not started
WF-17 | Workflow automation & approvals | Priya Sharma | 2026-05-24 | 2026-05-29 | 0% | Not started
WF-18 | User role config & permissions | James Liu | 2026-05-26 | 2026-05-30 | 0% | Not started
WF-19 | Create training materials & guides | Lisa Chen | 2026-05-22 | 2026-05-31 | 10% | In progress
WF-20 | Pilot migration with test data | Marcus Johnson | 2026-05-29 | 2026-06-01 | 0% | Not started
WF-21 | UAT Round 1 | Lisa Chen | 2026-05-31 | 2026-06-05 | 0% | Not started
WF-22 | Bug fixes & UAT feedback | Priya Sharma | 2026-06-02 | 2026-06-06 | 0% | Not started
WF-23 | UAT Round 2 — final validation | Lisa Chen | 2026-06-05 | 2026-06-06 | 0% | Not started
WF-24 | Lessons learned documentation | Rachel Torres | 2026-06-05 | 2026-06-06 | 0% | Not started
WF-25 | Project closure sign-off & handover | Rachel Torres | 2026-06-07 | 2026-06-07 | 0% | Not started
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Blank Template
| Simple Project Planner | [5 empty] | TOTAL TASKS | [6 empty] | COMPLETED | [6 empty] | IN PROGRESS | [6 empty] | NOT STARTED | [6 empty] | 🎢 Overall Progress |  |  | 0% |  |  | 0
| Task-based Roadmap: 8-week project lifecycle | [5 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
1
Project Details | Project Name |  |  |  | Start Date |  | 🎯 Project Objective
| Project Manager |  |  |  | End Date | [30 empty] | Completed | 0
| Department / Client |  | Created On |  | Duration | [30 empty] | In progress | 0
| Created By |  | Last Updated |  | Days Left | [30 empty] | Not started | 0
Task Table | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ID | Task Name | Assigned To | Start Date | End Date | Progress | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
Note: This is a free version of the template that allows you to manage up to 25 tasks and customize the project title and start date.
For full access, unlimited task rows, and a fully unlocked file with complete customization capabilities, please get our Premium Template at Analysistabs.org.
Analysistabs ® Premium Templates

## Instructions
Simple Project Plan 2026 - Instructions
FIELD | WHAT TO ENTER
Project Name | Enter your project name (e.g., Website Redesign, ERP Migration).
Project Manager | Name of the person managing this project.
Department / Client | Your department or client name.
Start Date | Auto-calculated. Do not edit (grey cell).
End Date | Auto-calculated. Do not edit (grey cell).
Duration | Auto-calculated. Do not edit (grey cell).
Days Left | Auto-calculated. Do not edit (grey cell).
🎯 Project Objective | 1-2 sentence project goal and measurable success criteria.
Created By | Name of the person who created this plan.
Created On | Date this plan was created (MM/DD/YYYY).
Last Updated | Date of last update (MM/DD/YYYY).
Task Table Columns
ID | Unique task identifier (e.g., WF-01). Keep sequential.
Task Name | Clear, action-oriented task description.
Assigned To | Team member responsible for this task.
Start Date | Task start date (MM/DD/YYYY).
End Date | Task end date (MM/DD/YYYY).
Progress | Enter manually (0% to 100%). Update daily.
Status | Auto-calculated. Do not edit.
Gantt Chart | Auto-generated from Start/End dates. Do not edit. Bars update automatically.
Grey / Locked Cells
Light grey cells | Contain formulas - auto-calculated from your entries.
Formula bar blank | By design - formulas are hidden for protection.
Cannot edit | These cells are locked. Only white cells are editable.
Tips
Phase rows | Bold colored rows are section headers. Enter tasks below them.
Dropdowns | Click cells with small arrows to see available options.
Dates | Use MM/DD/YYYY format for all date fields.
Progress | Enter manually (0% to 100%). Update daily as work progresses.
Status | Auto-calculated from Progress. 100%=Completed, 1-99%=In progress, 0%=Not started.
Save often | File > Save As to create backup versions.
Need More Features?
More tasks | FREE version supports 25 tasks. Premium = unlimited tasks with auto-expanding rows.
Longer Gantt | FREE = 5-week Gantt. Premium = 9-week dynamic view with zoom in/out.
Unlimited Projects | Premium supports unlimited project sheets with one-click duplication.
Fully Unlocked | All cells editable. No locked sheets, no hidden formulas, no restrictions.
Fully Customizable | Easily customize colors, layout, and fields to suit any project type or industry.
Get Premium Template | Visit analysistabs.org/product/simple-multiple-project-tracking-template-excel/
Excel PM Templates by PNRao ¦ Excelx.com ¦ Powered by Analysistabs®

## Free vs Premium
FREE vs PREMIUM COMPARISON
Feature | Free Template | Premium Templates
Project Scope | Single Project Only | Multiple & Unlimited Projects
Visual Themes | Standard Light Mode | Light & Dark Mode
Timeline View | 5-Week Static Sprint | 9-Week Dynamic View with Zoom In/Out
Smart Filtering | No Filtering | Filter by Project, Team Member, or Status
Edit Mode | Standard Input | One-Click Highlight for all Editable Cells
Custom Schedules | Standard Calendar | Advanced Weekend & Official Holiday Logic
Resource Tracking | Not Included | Resource Active Workload Heatmap
Timeline Tools | Basic View | Highlight Today, Weekends, Holidays, & Overdue
Capacity | 25 Task Records | Unlimited Tasks (Portfolio Scale)
Dashboard | 1 Simple Gauge | Full Executive Portfolio Dashboard
Formula Access | Locked & Protected | 100% Unlocked & Fully Customizable
Price | FREE | $49 (One-Time Payment)

## License
License Terms
4 | Analysistabs® License Agreement
Licensed Product: Single User License to Analysistabs® Project Management Template
Single User License: Allows 1 User – 2 Devices.
4 | Grant of Licenses
Purchase of our Premium Template(s) gives rights for one active user (1 customer who purchased our premium template(s)) to use the file(s).
4 | As an owner of this license
| • | You can make copies for your own use.
| • | You must first remove our brand before exporting sheets, pages, slides as PDF and printing the files.
| • | You can export our template sheets/pages/slides as PDF & share PDF with others
| • | You can print sheets, pages and slides and share the hard copies
| • | You can use the files in one or two devices of yours
| • | You can edit the files as needed (password provided for locked sheets), except for the ReadMe and License sheets, which are non-editable.
| • | You must not remove our copyright notices and Licence sheets from the Templates. Instead, you can hide this Sheet.
4 | NOT ALLOWED
| • | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others
| • | Copies should not be made by anyone other than license owner
| • | You cannot sell the files/templates commercially
| • | You cannot transfer the license to another person.
4 | Liability
Analysistabs® will not be liable for any damages due to any business decisions taken based on the templates.
We put our maximum efforts to build each of the templates to provide best value to your investment on our templates. We developed our templates by following best practices to create world-class and professional templates in every phase of the development.
We have tested thoroughly to ensure the accuracy of the templates. We are happy to hear from you, we value your feedback to add new features, templates or fix the bugs (if any). Please email your valuable feedback to info@analysistabs.com.
📜 View Detailed License & Terms

## Analysistabs (hidden)
1
DO NOT DELETE OR MODIFY THIS SHEET
WARNING — SYSTEM SHEET
This sheet is required for the template to function correctly.
It contains essential configuration used by formulas, conditional formatting,
Gantt chart rendering, progress bars, and KPI calculations.
| If this sheet is deleted or modified: | 1
| • Gantt chart bars will stop rendering | 1
| • Progress bars will show errors | 1
• KPI cards will display #REF! errors
• Conditional formatting will break
• Auto-calculated fields will stop working
This sheet will be hidden when the template is exported.
Users will not see this sheet in the downloaded file.
Analysistabs® ¦ Excelx.com ¦ Template Configuration Sheet