## Construction Budget
CONSTRUCTION BUDGET
Track every build phase — budgeted vs actual, variance, and cost per square foot — to keep the project on budget.
PROJECT | New Home Build
SQ FT | 2400
BUILD BUDGET | SPENT | VARIANCE | W/ CONTINGENCY
300000 | 264500 | 35500 | 330000
all phases | to date | positive = under | budget + 10%
BUILD PHASES & LINE ITEMS
PHASE / ITEM | BUDGET | ACTUAL | VARIANCE | % BUDGET
Permits & Fees | 8000 | 8500 | -500 | 2.667%
Site Prep & Excavation | 15000 | 16200 | -1200 | 5%
Foundation | 28000 | 27500 | 500 | 9.333%
Framing | 45000 | 46000 | -1000 | 15%
Roofing | 22000 | 21000 | 1000 | 7.333%
Windows & Doors | 18000 | 18500 | -500 | 6%
Plumbing | 16000 | 15500 | 500 | 5.333%
Electrical | 17000 | 17800 | -800 | 5.667%
HVAC | 14000 | 13500 | 500 | 4.667%
Insulation & Drywall | 20000 | 20000 | 0 | 6.667%
Interior Finishes | 42000 | 38000 | 4000 | 14%
Exterior & Siding | 24000 | 22000 | 2000 | 8%
Flooring | 19000 | 0 | 19000 | 6.333%
Landscaping | 12000 | 0 | 12000 | 4%
TOTAL | 300000 | 264500 | 35500 | 100%
CONTINGENCY & RESERVES
Recommended contingency (10%) |  |  | 30000
Budget + contingency |  |  | 330000
Spent + committed to date |  |  | 264500
Buffer still available |  |  | 65500
Project budget $300,000 ($125/sq ft) — $264,500 spent, $35,500 remaining.
Most over budget: Site Prep & Excavation by $1,200. Biggest phase: Framing (15%).
Free Construction Budget Template — Excelx.com
Want auto-tracking, a transaction log, and a live dashboard? Upgrade to the Pro version.
HOW TO USE THIS TEMPLATE
1. Start at the top — fill in the setup inputs (blue cells).
2. Enter your numbers in the blue input cells — blue cells are yours to edit.
3. Work through each section: Build Phases & Line Items, Phase / Item, Hvac, Contingency & Reserves.
4. The totals and KPI cards update automatically as you type.
5. Review Variance by phase — overruns early compound later.
TIPS
• Blue numbers are your inputs — change them freely. Black numbers are formulas; avoid typing over them.
• Rename or add categories by typing over the labels.
• Everything recalculates automatically — no setup needed.

## Premium Preview
Free vs Pro — Construction Budget
WHAT YOU GET | FREE | PRO ⭐
DASHBOARD & VISUALS
Live chart (auto-updating) | — | ✓
Spend by phase chart | — | ✓
Cost per sq ft | — | ✓
Remaining-budget tracker | — | ✓
INSIGHTS
Phase-wise breakdown | — | ✓
Contingency check | — | ✓
KPI summary cards | ✓ | ✓
PLAN & CUSTOMISE
Construction line items | ✓ | ✓
Budget vs actual | ✓ | ✓
Notes | ✓ | ✓
Fully unlocked — edit formulas & add rows | — | ✓
Free lifetime updates | — | ✓
YOUR SCORE | 4 of 12 | 12 of 12
🚀 Get Pro Now →
Instant download · Fully unlocked & customizable · Keep it forever
🎁 BEST VALUE — Bundle Offer
The Life OS Bundle — All-in-One Excel System
Budgeting & Personal Finance · Life Planners & Calendars ADHD Focus · Meal Prep & Workouts
200+ unique templates · 300+ worksheets
across 15 products for the price of 2 — save $865 today!
One-time payment · Lifetime access · Free updates
🎁 Grab the Bundle — Save $865 →
Free & Premium Budget Templates — Developed by PNRao ¦ Excelx.com ¦ Analysistabs®

## License-Disclaimer
License Terms
4 | Analysistabs® License Agreement
This Template/Excel File and sample data is created by Excelx.com Powered by Analysistabs®
4 | Single User License: Allows 1 user (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this file/template for their personal use only
4 | You can share the web page link:(https://excelx.com/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | Excel Files/ templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
4 | Disclaimer
4 | The information and templates on Excelx.com are provided “as is”, for personal reference only. We strive for accuracy but cannot guarantee it — you use this template at your own risk and take full responsibility for any outcome. Excelx.com / Analysistabs® accepts no liability for any loss or damage arising from its use.
4 | For personal budgeting and educational purposes only — it does not constitute financial, tax, legal, or investment advice.