## Home Renovation Budget
HOME RENOVATION BUDGET
Track every renovation cost against estimate, monitor payments, and hold a contingency.
PROJECT | Kitchen Remodel
YEAR | 2026
Today: July 22, 2026
ESTIMATED | ACTUAL | PAID SO FAR | STILL TO PAY
32500 | 31150 | 12400 | 18750
planned reno cost | current cost | paid to date | remaining balance
PLANNING & PREP
ITEM | ESTIMATED | ACTUAL | PAID | BALANCE
Design & Permits | 2000 | 2100 | 2100 | 0
Demolition | 1500 | 1400 | 1400 | 0
Subtotal | 3500 | 3500 | 3500 | 0
STRUCTURE & SYSTEMS
ITEM | ESTIMATED | ACTUAL | PAID | BALANCE
Structural / Framing | 3000 | 3200 | 1600 | 1600
Plumbing | 2500 | 2500 | 1000 | 1500
Electrical | 2200 | 2300 | 1000 | 1300
Subtotal | 7700 | 8000 | 3600 | 4400
SURFACES & FINISHES
ITEM | ESTIMATED | ACTUAL | PAID | BALANCE
Flooring | 4000 | 3800 | 1900 | 1900
Walls & Paint | 1800 | 1750 | 900 | 850
Countertops | 3000 | 3100 | 0 | 3100
Subtotal | 8800 | 8650 | 2800 | 5850
CABINETS, APPLIANCES & EXTRAS
ITEM | ESTIMATED | ACTUAL | PAID | BALANCE
Kitchen Cabinets | 5000 | 5000 | 2500 | 2500
Appliances | 3500 | 3400 | 0 | 3400
Fixtures & Lighting | 1500 | 1600 | 0 | 1600
Contingency (10%) | 2500 | 1000 | 0 | 1000
Subtotal | 12500 | 11000 | 2500 | 8500
GRAND TOTAL | 32500 | 31150 | 12400 | 18750
Free Home Renovation Budget Template — Excelx.com
Want auto-tracking, a transaction log, and a live dashboard? Upgrade to the Pro version.
HOW TO USE THIS TEMPLATE
1. Start at the top — fill in the setup inputs (blue cells).
2. Enter your numbers in the blue input cells — blue cells are yours to edit.
3. Work through each section: Planning & Prep, Structure & Systems, Surfaces & Finishes, Cabinets, Appliances & Extras.
4. The totals and KPI cards update automatically as you type.
5. Review Still To Pay and each room subtotal as work progresses.
TIPS
• Blue numbers are your inputs — change them freely. Black numbers are formulas; avoid typing over them.
• Rename or add categories by typing over the labels.
• Everything recalculates automatically — no setup needed.

## Premium Preview
Free vs Pro — Home Renovation Budget
WHAT YOU GET | FREE | PRO ⭐
DASHBOARD & VISUALS
Live chart (auto-updating) | — | ✓
Spend by Section chart | — | ✓
Renovation insights | — | ✓
% spent gauge | — | ✓
INSIGHTS
Balance-due tracker | — | ✓
Contingency check | — | ✓
KPI summary cards | ✓ | ✓
PLAN & CUSTOMISE
Renovation categories | ✓ | ✓
Budget vs actual | ✓ | ✓
Notes & to-dos | ✓ | ✓
Fully unlocked — edit formulas & add rows | — | ✓
Free lifetime updates | — | ✓
YOUR SCORE | 4 of 12 | 12 of 12
🚀 Get Pro Now →
Instant download · Fully unlocked & customizable · Keep it forever
🎁 BEST VALUE — Bundle Offer
The Life OS Bundle — All-in-One Excel System
Budgeting & Personal Finance · Life Planners & Calendars ADHD Focus · Meal Prep & Workouts
200+ unique templates · 300+ worksheets
across 15 products for the price of 2 — save $865 today!
One-time payment · Lifetime access · Free updates
🎁 Grab the Bundle — Save $865 →
Free & Premium Budget Templates — Developed by PNRao ¦ Excelx.com ¦ Analysistabs®

## License-Disclaimer
License Terms
4 | Analysistabs® License Agreement
This Template/Excel File and sample data is created by Excelx.com Powered by Analysistabs®
4 | Single User License: Allows 1 user (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this file/template for their personal use only
4 | You can share the web page link:(https://excelx.com/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | Excel Files/ templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
4 | Disclaimer
4 | The information and templates on Excelx.com are provided “as is”, for personal reference only. We strive for accuracy but cannot guarantee it — you use this template at your own risk and take full responsibility for any outcome. Excelx.com / Analysistabs® accepts no liability for any loss or damage arising from its use.
4 | For personal budgeting and educational purposes only — it does not constitute financial, tax, legal, or investment advice.