## 95 Marketing Content Calendar
X. |  | MARKETING & CONTENT CALENDAR · 2027 | [12 empty] | CONTENT PIPELINE
ExcelX |  | A publishing pipeline, not a month grid — pick Channel, Type and Status from the dropdowns; the status board, channel mix and monthly output all recount themselves
# | PUBLISH |  | WK | TITLE |  |  | CHANNEL | TYPE |  | CAMPAIGN | OWNER | STATUS |  | LIVE |  | NOTES / CTA
1 | 2027-01-05 |  | 1 | New Year, New Ops — hero blog |  |  | Blog | Article |  | Q1 Launch | Sam | Published |  | TRUE |  | Pillar page, 1,800 words
2 | 2027-01-09 |  | 1 | Product roadmap 2027 webinar |  |  | Webinar | Live |  | Q1 Launch | Alex | Published |  | TRUE |  | Registration LP + 3 reminder emails
3 | 2027-01-16 |  | 2 | LinkedIn carousel — 5 trends |  |  | LinkedIn | Carousel |  | Q1 Launch | Riley | Published |  | TRUE |  | Repurpose from hero blog
4 | 2027-01-23 |  | 3 | Customer story: Northwind |  |  | Blog | Case study |  | Always-on | Sam | Published |  | TRUE |  | Needs legal sign-off
5 | 2027-01-30 |  | 4 | February newsletter |  |  | Email | Newsletter |  | Always-on | Jordan | Published |  | TRUE |  | Segment: active users
6 | 2027-02-06 |  | 5 | Pricing page refresh |  |  | Website | Landing page |  | Q1 Launch | Alex | Scheduled |  | FALSE |  | A/B test two headlines
7 | 2027-02-20 |  | 7 | Short-form video: onboarding |  |  | YouTube | Video |  | Activation | Riley | Scheduled |  | FALSE |  | 60 seconds, vertical
8 | 2027-03-06 |  | 9 | Integration launch — press release |  |  | PR | Press release |  | Partner push | Jordan | Scheduled |  | FALSE |  | Embargo until 9am ET
9 | 2027-03-13 |  | 10 | March newsletter |  |  | Email | Newsletter |  | Always-on | Jordan | Review |  | FALSE |  | Include integration news
10 | 2027-03-20 |  | 11 | Benchmark report 2027 |  |  | Gated | Report |  | Demand gen | Sam | Review |  | FALSE |  | Design pass pending
11 | 2027-04-03 |  | 13 | LinkedIn thought-leadership post |  |  | LinkedIn | Post |  | Always-on | Alex | Draft |  | FALSE
12 | 2027-04-10 |  | 14 | Spring campaign teaser |  |  | Instagram | Reel |  | Q2 Spring | Riley | Draft |  | FALSE |  | Shoot booked 12 Apr
13 | 2027-04-24 |  | 16 | Spring campaign launch email |  |  | Email | Campaign |  | Q2 Spring | Jordan | Draft |  | FALSE |  | 3-email sequence
14 | 2027-05-08 |  | 18 | How-to guide: reporting |  |  | Blog | Guide |  | Activation | Sam | Draft |  | FALSE |  | SEO target: excel reporting
15 | 2027-05-22 |  | 20 | Partner co-marketing webinar |  |  | Webinar | Live |  | Partner push | Alex | Idea |  | FALSE |  | Confirm partner slot
16 | 2027-06-05 |  | 22 | Mid-year customer survey |  |  | Email | Survey |  | Always-on | Jordan | Idea |  | FALSE
17 | 2027-06-19 |  | 24 | H1 results infographic |  |  | LinkedIn | Infographic |  | Always-on | Riley | Idea |  | FALSE
18 | 2027-07-03 |  | 26 | Summer feature announcement |  |  | Blog | Announcement |  | Q3 Summer | Sam | Idea |  | FALSE
19 | 2027-07-17 |  | 28 | Video testimonial series ep.1 |  |  | YouTube | Video |  | Demand gen | Riley | Idea |  | FALSE
20 | 2027-07-31 |  | 30 | August newsletter |  |  | Email | Newsletter |  | Always-on | Jordan | Idea |  | FALSE
21 | 2027-08-14 |  | 32 | Back-to-work productivity guide |  |  | Gated | Guide |  | Demand gen | Sam | Idea |  | FALSE
22 | 2027-08-28 |  | 34 | Q4 planning webinar |  |  | Webinar | Live |  | Q4 Renewal | Alex | Idea |  | FALSE
23 | 2027-09-11 |  | 36 | Customer story: Contoso |  |  | Blog | Case study |  | Always-on | Sam | Idea |  | FALSE
24 | 2027-09-25 |  | 38 | Renewal reminder sequence |  |  | Email | Campaign |  | Q4 Renewal | Jordan | Idea |  | FALSE
25 | 2027-10-09 |  | 40 | Year in review infographic |  |  | LinkedIn | Infographic |  | Always-on | Riley | Idea |  | FALSE
26 | 2027-10-23 |  | 42 | Black Friday offer page |  |  | Website | Landing page |  | Q4 Renewal | Alex | Idea |  | FALSE
27 | 2027-11-06 |  | 44 | December newsletter |  |  | Email | Newsletter |  | Always-on | Jordan | Idea |  | FALSE
28 | 2027-11-20 |  | 46 | 2028 predictions blog |  |  | Blog | Article |  | Q4 Renewal | Sam | Idea |  | FALSE
29 | 2027-12-04 |  | 48 | Holiday thank-you video |  |  | YouTube | Video |  | Always-on | Riley | Idea |  | FALSE
30 | 2027-12-18 |  | 50 | 2028 planning kit |  |  | Gated | Template |  | Demand gen | Alex | Idea |  | FALSE
31 | 2027-12-25 |  | 51 | New Year countdown posts |  |  | Instagram | Post |  | Always-on | Riley | Idea |  | FALSE
STATUS BOARD | [5 empty] | CHANNEL MIX |  |  |  |  | MONTHLY OUTPUT
Idea |  |  |  | 17 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | Blog |  |  | 6 | ¦¦¦¦¦¦ | Jan / Feb |  | 7 | 5 live |  |  | ¦¦¦¦¦¦¦
Draft |  |  |  | 4 | ¦¦¦¦ | Email |  |  | 7 | ¦¦¦¦¦¦¦ | Mar / Apr |  | 6 | 0 live |  |  | ¦¦¦¦¦¦
Review |  |  |  | 2 | ¦¦ | LinkedIn |  |  | 4 | ¦¦¦¦ | May / Jun |  | 4 | 0 live |  |  | ¦¦¦¦
Scheduled |  |  |  | 3 | ¦¦¦ | Webinar |  |  | 3 | ¦¦¦ | Jul / Aug |  | 5 | 0 live |  |  | ¦¦¦¦¦
Published |  |  |  | 5 | ¦¦¦¦¦ | YouTube |  |  | 3 | ¦¦¦ | Sep / Oct |  | 4 | 0 live |  |  | ¦¦¦¦
[6 empty] | Instagram |  |  | 2 | ¦¦ | Nov / Dec |  | 5 | 0 live |  |  | ¦¦¦¦¦
The pipeline holds 31 pieces across 9 channels — 5 published, 3 scheduled, 6 in production and 17 still at idea stage.
Busiest owner: Sam. Next item due: Tue 5 Jan — New Year, New Ops — hero blog.
Free 2027 Marketing & Content Calendar — by Excelx.com Powered by Analysistabs® · pipeline, status board, channel mix · sized for Letter & A4 | [10 empty] | Get Premium Templates at Analysistabs®
PREMIUM Premium Calendars and Planners
Type a year and the grid rebuilds, plus planners with dashboards. Unlocked, formula-driven, lifetime updates.
Browse the premium suite on Analysistabs.org >
Also free at Excelx.com: 100+ yearly, monthly, weekly and daily calendars; week-number and fiscal-year layouts; wall planners; leave, payroll and shift trackers; project timelines; academic planners; and 2027 public holiday calendars for 65 countries.
Browse all 2027 calendar templates >
Need a different version?
Monday / Sunday start - Letter / A4 - other years
excelx.com/template/calendar/2027y/

## More Templates
Free templates first, premium suites below. No sign-up, no email, no macros.
FREE TEMPLATES
Always free, no sign-up. Every layout is unlocked and ready to print.
All Free Excel Templates | The full free library - calendars, planners, trackers and more.
Calendar Templates - every year and format | Every year and format: yearly, monthly, weekly and daily.
2027 Calendar Templates | All 2027 layouts - portrait, landscape, Sunday or Monday start.
Project Management Templates | Gantt charts, task trackers, timelines and status reports.
Budget Templates | Monthly, annual and personal budgets with built-in charts.
PREMIUM TEMPLATES - built to save you the setup
Unlocked, formula-driven, lifetime updates. Trusted in 100+ countries.
Premium Calendars and Planners | Type a year and the grid rebuilds, plus planners with dashboards.
Project Management Suite | Auto-shifting Gantt, resource and milestone tracking.
Budget & Finance Suite | Automated categories, charts and cashflow forecasting.
All Premium Templates | Premium Templates for Project Management, Finance & Life.
LICENCE
You MAY | Use this file for personal or business purposes. Edit it, print it, and share it inside your organisation.
You MAY NOT | Resell, redistribute, or republish this file or any part of it, on any website, marketplace or storefront, with or without modification.
Attribution | This file and its layout are the copyright of Excelx.com, powered by Analysistabs®. Removing the credit row does not transfer ownership.
Report misuse | info@analysistabs.com
© Excelx.com - All rights reserved. | Powered by Analysistabs®
Excelx.com - Free Excel Templates
Excelx.com
Analysistabs.org
Analysistabs®