## 101 Project Timeline Gantt
X. |  | PROJECT TIMELINE (GANTT CHART) · 2027 | [15 empty] | AUTO BARS
ExcelX |  | Type a start and end date and the bar draws itself across the month columns — no manual shading. Progress, slip against today and the critical path flag all calculate.
PROJECT |  |  | Website replatform | [5 empty] | STATUS DATE |  |  | 2027-06-30 |  |  |  |  | bars shade any month the task touches
# | TASK |  |  | OWNER | START | END | DAYS | DONE % | STATUS | J | F | M | A | M | J | J | A | S | O | N | D | SLIP
1 | Discovery & requirements |  |  | Sam | 2027-01-15 | 2027-02-26 | 31 | 100% | Complete | bar: J to F
2 | Vendor selection |  |  | Alex | 2027-02-01 | 2027-03-12 | 30 | 100% | Complete | bar: F to 2027-06-30 M
3 | Information architecture |  |  | Riley | 2027-03-01 | 2027-04-09 | 30 | 100% | Complete | bar: 2027-06-30 M to 2027-06-30 A
4 | Visual design system |  |  | Riley | 2027-04-05 | 2027-05-28 | 40 | 90% | Overdue | bars shade any month the task touches SLIP: 33d
5 | Content audit & migration plan |  |  | Jordan | 2027-04-01 | 2027-06-30 | 65 | 70% | In progress | bar: 2027-06-30 A to 2027-06-30 J
6 | Backend build — core |  |  | Priya | 2027-05-03 | 2027-09-30 | 109 | 45% | In progress | bar: 2027-06-30 M to bars shade any month the task touches S
7 | CMS setup & templates |  |  | Tom | 2027-06-01 | 2027-08-31 | 66 | 40% | In progress | bar: 2027-06-30 J to bars shade any month the task touches A
8 | Front-end build |  |  | Nina | 2027-07-01 | 2027-10-29 | 87 | 25% | In progress | bar: 2027-06-30 J to bars shade any month the task touches O
9 | SEO redirect mapping |  |  | Jordan | 2027-08-02 | 2027-09-30 | 44 | 10% | In progress | bar: bars shade any month the task touches A to bars shade any month the task touches S
10 | Integrations — CRM & analytics |  |  | Marcus | 2027-09-01 | 2027-10-29 | 43 | 0% | Not started | bar: bars shade any month the task touches S to bars shade any month the task touches O
11 | Accessibility audit |  |  | Ava | 2027-10-04 | 2027-10-29 | 20 | 0% | Not started | bar: bars shade any month the task touches O
12 | QA & bug fixing |  |  | Tom | 2027-10-11 | 2027-11-30 | 37 | 0% | Not started | bar: bars shade any month the task touches O to bars shade any month the task touches N
13 | Content load |  |  | Jordan | 2027-11-01 | 2027-11-30 | 22 | 0% | Not started | bar: bars shade any month the task touches N
14 | UAT & sign-off |  |  | Sam | 2027-11-15 | 2027-12-10 | 20 | 0% | Not started | bar: bars shade any month the task touches N to bars shade any month the task touches D
15 | Launch & DNS cutover |  |  | Alex | 2027-12-13 | 2027-12-17 | 5 | 0% | Not started | bar: bars shade any month the task touches D
16 | Hypercare & handover |  |  | Marcus | 2027-12-20 | 2027-12-31 | 10 | 0% | Not started | bar: bars shade any month the task touches D
PROJECT TOTALS → | [6 empty] | 659 | 41.59% | 1 overdue
Sixteen tasks, 659 working days of effort, 42% complete weighted by duration as at 30 Jun 2027. 1 task is past its end date and still open; 5 are in flight.
Bars draw from the START and END dates — green where the task is complete, red where it has slipped past the status date, blue where it is still open. Move the STATUS DATE to re-assess the whole plan.
Free 2027 Project Timeline & Gantt Chart — by Excelx.com Powered by Analysistabs® · formula-driven bars, no manual shading · sized for Letter & A4 | [9 empty] | 2027-06-30 M: Get Premium Templates at Analysistabs®
PREMIUM Premium Calendars and Planners
Type a year and the grid rebuilds, plus planners with dashboards. Unlocked, formula-driven, lifetime updates.
Browse the premium suite on Analysistabs.org >
Also free at Excelx.com: 100+ yearly, monthly, weekly and daily calendars; week-number and fiscal-year layouts; wall planners; leave, payroll and shift trackers; project timelines; academic planners; and 2027 public holiday calendars for 65 countries.
Browse all 2027 calendar templates >
Need a different version?
Monday / Sunday start - Letter / A4 - other years
excelx.com/template/calendar/2027y/

## More Templates
Free templates first, premium suites below. No sign-up, no email, no macros.
FREE TEMPLATES
Always free, no sign-up. Every layout is unlocked and ready to print.
All Free Excel Templates | The full free library - calendars, planners, trackers and more.
Calendar Templates - every year and format | Every year and format: yearly, monthly, weekly and daily.
2027 Calendar Templates | All 2027 layouts - portrait, landscape, Sunday or Monday start.
Project Management Templates | Gantt charts, task trackers, timelines and status reports.
Budget Templates | Monthly, annual and personal budgets with built-in charts.
PREMIUM TEMPLATES - built to save you the setup
Unlocked, formula-driven, lifetime updates. Trusted in 100+ countries.
Premium Calendars and Planners | Type a year and the grid rebuilds, plus planners with dashboards.
Project Management Suite | Auto-shifting Gantt, resource and milestone tracking.
Budget & Finance Suite | Automated categories, charts and cashflow forecasting.
All Premium Templates | Premium Templates for Project Management, Finance & Life.
LICENCE
You MAY | Use this file for personal or business purposes. Edit it, print it, and share it inside your organisation.
You MAY NOT | Resell, redistribute, or republish this file or any part of it, on any website, marketplace or storefront, with or without modification.
Attribution | This file and its layout are the copyright of Excelx.com, powered by Analysistabs®. Removing the credit row does not transfer ownership.
Report misuse | info@analysistabs.com
© Excelx.com - All rights reserved. | Powered by Analysistabs®
Excelx.com - Free Excel Templates
Excelx.com
Analysistabs.org
Analysistabs®